## PI Q1 21-22
Record Number | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
1 | 19/LO/0546 | 250345 | Effectiveness and cost-effectiveness of inspiratory muscle training (IMT) for reducing postoperative pulmonary complications (PPC): a sham-controlled randomised controlled trial (RCT) (INSPIRE) | 2021-05-25 | 2020-01-13 | 2021-01-10 | 2019-05-16 | 2021-03-10 | 2021-04-29 | 2021-05-13 | Sponsor
2 | 21/HRA/0645 | 296247 | A Randomized, Observer-Blind, Placebo-Controlled, Phase 2/3 Study to Assess the Safety, Efficacy, and Immunogenicity of a Recombinant Coronavirus-Like Particle COVID-19 Vaccine in Adults 18 Years of Age or Older |  | 2021-02-10 | 2021-04-22 | 2021-04-07 | 2021-04-23 | 2021-04-26 |  | Sponsor
3 | 20/LO/0196 | 271343 | PreOperative Endocrine Therapy for Individualised Care with Abemaciclib | 2020-12-22 | 2020-09-22 | 2020-09-22 | 2020-07-08 | 2020-11-13 | 2020-11-19 | 2020-12-04 | NHS provider
4 | 20/NI/0128 | 273402 | A PHASE III, RANDOMISED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY AND SAFETY OF GDC-0077 PLUS PALBOCICLIB AND FULVESTRANT VERSUS PLACEBO PLUS PALBOCICLIB AND FULVESTRANT IN PATIENTS WITH PIK3CA-MUTANT, HORMONE RECEPTORPOSITIVE, HER2-NEGATIVE LOCALLY ADVANCED OR METASTATIC BREAST CANCER |  | 2019-10-24 | 2021-03-12 | 2020-11-27 | 2021-05-26 | 2021-06-08 | 2021-06-18 | NHS provider
5 | 20/LO/0963 | 281310 | Randomized, double-blind, phase 3 study of tucatinib or placebo in combination with ado-trastuzumab emtansine (T-DM1) for subjects with unresectable locally-advanced or metastatic HER2+ breast cancer. | 2021-04-26 | 2020-01-31 | 2021-03-05 | 2020-10-23 | 2021-03-03 | 2021-03-09 | 2021-03-26
6 | 20/LO/0322 | 275926 | A Phase III Double-blind Randomised Study Assessing the Efficacy and Safety of Capivasertib + Fulvestrant Versus Placebo + Fulvestrant as Treatment for Locally Advanced (Inoperable) or Metastatic Hormone Receptor Positive, Human Epidermal Growth Factor Receptor 2 Negative (HR+/HER2−) Breast Cancer Following Recurrence or Progression On or After Treatment with an Aromatase Inhibitor (CAPItello-291) | 2020-12-21 | 2020-02-25 | 2020-10-22 | 2020-05-04 | 2020-10-23 | 2020-10-26 | 2020-12-01
7 | 20/LO/0739 | 278092 | An Open-Label Multicenter Phase 1b Study of H3B-6545 in Combination With Palbociclib in Women With Advanced or Metastatic Estrogen Receptor–Positive HER2-Negative Breast Cancer | 2021-06-30 | 2020-01-07 | 2020-12-04 | 2020-09-21 | 2021-05-26 | 2021-05-26 | 2021-06-03 | Sponsor
8 | 19/NI/0126 | 254829 | SMALL: A Phase III, randomised, multi-centre trial addressing overtreatment of small screen-detected breast cancer by comparing standard surgery versus minimally invasive vacuum-assisted excision |  | 2019-09-15 | 2021-04-08 | 2019-10-15 | 2021-03-12 | 2021-04-26 | 2021-05-13 | Neither
9 | 20/LO/1114 | 1003435 | A PHASE III RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY EVALUATING THE EFFICACY AND SAFETY OF GDC-9545 COMBINED WITH PALBOCICLIB COMPARED WITH LETROZOLE COMBINED WITH PALBOCICLIB IN PATIENTS WITH ESTROGEN RECEPTOR-POSITIVE, HER2-NEGATIVE LOCALLY ADVANCED OR METASTATIC BREAST CANCER |  | 2020-09-07 | 2021-06-08 | 2020-12-08 | 2021-06-03 | 2021-06-08 | 2021-06-14
10 | 20/EE/0189 | 271212 | Adaptive Phase I/II Open-Label, Dose-Finding Study of The Anti-IL23 Targeting Monoclonal Antibody Tildrakizumab Administered In Combination With Abiraterone Acetate In Men Suffering From Metastatic Castration-Resistant Prostate Cancer (mCRPC) | 2021-01-12 | 2020-08-14 | 2020-09-16 | 2020-10-20 | 2020-11-17 | 2020-11-18 | 2020-11-18 | Neither
11 | 20/LO/0334 | 270978 | A PHASE Ia/Ib OPEN-LABEL, DOSE-ESCALATION STUDY OF THE SAFETY AND PHARMACOKINETICS OF STA551 AS A SINGLE AGENT AND IN COMBINATION WITH ATEZOLIZUMAB IN PATIENTS WITH LOCALLY ADVANCED OR METASTATIC SOLID TUMORS | 2020-08-28 | 2019-12-19 | 2020-07-14 | 2020-05-06 | 2020-07-20 | 2020-07-23 | 2020-08-05
12 | 20/LO/0683 | 282711 | A first-in-human, two part, open-label, clinical study to assess the safety, tolerability and activity of intravenous doses or ICT01 as monotherapy and in combination with an immune checkpoint inhibitor, in patients with advanced-stage, relapsed/refractory cancer (EVICTION Study) |  | 2020-04-20 | 2020-09-29 | 2020-07-20 | 2020-07-17 | 2020-11-18 | 2020-11-20 | Sponsor
13 | 20/LO/0696 | 276806 | A Phase 1 Study of SGN-TGT in Subjects with Advanced Malignancies | 2020-12-16 | 2020-04-28 | 2020-10-13 | 2020-07-01 | 2020-10-22 | 2020-10-23 | 2020-11-03
14 | 21/LO/0053 | 285061 | A Phase 1b Study Evaluating the Safety and Efficacy of AMG 160 in Combination With Enzalutamide in Subjects With Metastatic Castration- |  | 2020-12-18 | 2021-05-24 | 2021-04-08 | 2021-06-16 | 2021-06-24
15 | 17/NW/0053 | 284885 | A Phase 1 Study of SGN-B6A in Advanced Solid Tumors |  | 2020-08-07 | 2020-11-12 | 2020-12-01 | 2021-01-14 | 2021-01-18 | 2021-02-22 | Sponsor
16 | 20/LO/1081 | 287766 | An Open-label, Multicenter, Dose Escalation Phase 1b Study to Assess the Safety and Pharmacokinetics of Subcutaneous Delivery of Amivantamab, a Human Bispecific EGFR and cMet Antibody for the Treatment of Advanced Solid Malignancies | 2021-01-06 | 2020-08-27 | 2020-10-29 | 2020-10-16 | 2020-12-17 | 2020-12-21 | 2021-01-06
17 | 20/LO/1287 | 279624 | A Phase 1 Open-Label, Dose Escalation and Expansion Trial to Investigate the Safety, Pharmacokinetics and Pharmacodynamics of CB307, a Trispecific Humabody T-cell Enhancer, in Patients with PSMA+ Advanced and/or Metastatic Solid Tumours (POTENTIA) |  | 2020-12-04 | 2021-03-24 | 2021-02-01 | 2021-03-25 | 2021-03-29 | 2021-03-30 | Neither
18 | 20/LO/1235 | 289189 | A Phase 1, Open-label, Dose-escalation Study of the PI3K Inhibitor SL-901 in Patients with Advanced Solid Tumors | 2021-03-19 | 2020-11-12 | 2021-01-06 | 2021-01-07 | 2021-03-01 | 2021-03-02 | 2021-03-18 | Nhs provider
19 | 21/LO/0331 | 295691 | A Phase 1 Study of SGN-STNV in Advanced Solid Tumors |  | 2021-04-07 | 2021-05-27 | 2021-05-19 | 2021-06-22 | 2021-06-30
20 | 19/SC/0597 | 264344 | A Phase 2, Multicenter Open-Label, Non-randomized study of Bavituximab plus Pembrolizumab in patients with advanced gastric or gastroesophageal cancer who have progressed on or after at least one prior standard therapy. | 2020-10-26 | 2019-04-29 | 2020-08-25 | 2020-01-21 | 2020-08-14 | 2020-08-27 | 2020-10-02
21 | 19/LO/1541 | 271255 | Open-Label Phase 2 Study of Ladiratuzumab Vedotin (LV) for Unresectable Locally Advanced or Metastatic Solid Tumors |  | 2019-07-30 | 2021-05-10 | 2019-11-29 | 2021-04-15 | 2021-05-20 | 2021-06-22
22 | 19/LO/1449 | 269837 | Phase 3 Study of Gemcitabine/Cisplatin ± Pembrolizumab as First-line Therapy of Advanced/Unresectable Biliary Tract Carcinoma | 2021-01-26 | 2019-11-14 | 2020-09-14 | 2020-03-24 | 2020-10-08 | 2020-11-05 | 2020-11-11 | Neither
23 | 20/NW/0054 | 274432 | A Randomized, Double-blind, Placebo-controlled Phase 3 Trial of Pembrolizumab (MK-3475) Versus Placebo in Participants with Esophageal Carcinoma Receiving Concurrent Definitive Chemoradiotherapy (KEYNOTE 975) | 2021-01-18 | 2020-02-03 | 2020-09-29 | 31/3/202 | 2020-10-02 | 2020-11-06 | 2020-12-02 | Neither
24 | 20/NW/0134 | 265626 | A Phase 3 Multicenter, Open-Label, Randomized, Controlled Study of Oral Infigratinib versus Gemcitabine with Cisplatin in Subjects with Advanced/Metastatic or Inoperable Cholangiocarcinoma with FGFR2 Gene Fusions/Translocations: The PROOF Trial |  | 2019-08-30 | 2020-09-28 | 2020-07-08 | 2020-10-06 | 2020-10-14 | 2021-01-08 | Sponsor
25 | 18/SC/0583 | 238087 | A Phase 1 trial of the safety, tolerability and biological effects of intravenous Enadenotucirev, a novel oncolytic virus, in combination with chemoradiotherapy in locally advanced rectal cancer |  | 2020-05-14 | 2021-03-12 | 2020-09-25 | 2021-04-23 | 2021-04-27 |  | Sponsor
26 | 20/EM/0087 | 274214 | An open-label, randomised, multicentre, phase III study of irinotecan liposome injection, oxaliplatin, 5-fluorouracil/leucovorin versus nab-paclitaxel plus gemcitabine in subjects who have not previously received chemotherapy for metastatic adenocarcinoma of the pancreas. | 2021-02-19 | 2019-10-28 | 2020-12-07 | 2020-05-19 | 2021-01-28 | 2021-02-09 | 2021-02-18 | Sponsor
27 | 20/EM/0160 | 282796 | A Global, Multicenter, Randomized, Placebocontrolled Phase 3 Trial To Compare The Efficacy And Safety Of Fruquintinib Plus Best Supportive Care To Placebo Plus Best Supportive Care In Patients With Refractory Metastatic Colon Cancer (Fresco-2) |  | 2020-06-11 | 2021-02-11 | 2021-02-11 | 2021-04-22 | 2021-05-14 |  | Sponsor
28 | 20/NE/0201 | 286160 | A Phase 3 Global, Multicenter, Double-Blind Randomized Study of Carboplatin-Paclitaxel With INCMGA00012 or Placebo in Participants With Inoperable Locally Recurrent or Metastatic Squamous Cell Carcinoma of the Anal Canal Not Previously Treated With Systemic Chemotherapy (POD1UM-303/InterAACT 2) | 2021-01-15 | 2020-06-03 | 2021-01-06 | 2020-11-02 | 2021-01-07 | 2021-01-12 | 2021-01-15
29 | 20/SC/0326 | 286972 | A Randomized, Open-Label, Phase 3 Trial of Epcoritamab vs Investigator’s Choice Chemotherapy in Relapsed/Refractory Diffuse Large B-cell Lymphoma | 2021-06-29 | 2020-08-10 | 2021-01-29 | 2021-01-11 | 2021-02-24 | 2021-03-02 | 2021-04-26 | Neither
30 | 20/SC/0371 | 286893 | A PHASE III, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY OF ATEZOLIZUMAB WITH OR WITHOUT TIRAGOLUMAB (ANTI-TIGIT ANTIBODY) IN PATIENTS WITH UNRESECTABLE LOCALLY ADVANCED ESOPHAGEAL SQUAMOUS CELL CARCINOMA | 2021-05-25 | 2020-07-15 | 2020-12-15 | 2020-12-09 | 2020-12-17 | 2020-12-17 | 2021-01-15 | Neither
31 | 20/WS/0140 | 285076 | A Phase II single-arm study to investigate tepotinib combined with cetuximab in RAS/BRAF wild-type left-sided metastatic colorectal cancer (mCRC) patients having acquired resistance to anti-EGFR antibody targeting therapy due to MET amplification |  | 2020-06-16 | 2021-05-06 | 2020-09-25 | 2021-06-24 | 2021-06-24 | 2021-06-30
32 | 20/NE/0263 | 289706 | A Multi-indication, Single-treatment Arm, Open-label Phase 2 Study of Regorafenib and Nivolumab in Combination in Patients with Recurrent or Metastatic Solid Tumors | 2021-04-06 | 2020-11-11 | 2020-12-15 | 2021-03-17 | 2021-03-12 | 2021-03-16 | 2021-03-17 | Neither
33 | 20/NW/0448 | 1003497 | A PHASE II, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY OF ATEZOLIZUMAB WITH OR WITHOUT BEVACIZUMAB IN COMBINATION WITH CISPLATIN + GEMCITABINE IN PATIENTS WITH UNTREATED, ADVANCED BILIARY TRACT CANCER |  | 2021-01-18 | 2021-06-28 | 2021-02-01 | 2021-06-28 | 2021-06-29
34 | 21/LO/0033 | 1003213 | A Randomized, Phase 3, Double-Blind Study of Chemoradiotherapy With or Without Pembrolizumab for the Treatment of High-risk, Locally Advanced Cervical Cancer (KEYNOTE-A18 / ENGOT-cx11) |  | 2020-02-14 | 2021-03-31 | 2021-03-30 | 2021-04-08 | 2021-04-16 | 2021-05-24 | Neither
35 | 20/LO/0957 | 276634 | MIRASOL: A Randomized, Open-label, Phase 3 Study of Mirvetuximab Soravtansine vs. Investigator’s Choice of Chemotherapy in Advanced High-Grade Epithelial Ovarian, Primary Peritoneal, or Fallopian Tube Cancers with High Folate Receptor-Alpha Expression | 2021-03-17 | 2020-04-20 | 2020-11-11 | 2020-11-06 | 2021-01-28 | 2021-01-29 | 2021-02-25 | Sponsor
36 | 21/NW/0116 | 1003450 | A Phase II, Multicenter, Open-label Study to Evaluate the Efficacy and Safety of Trastuzumab Deruxtecan (T-DXd, DS-8201a) for the Treatment of Selected HER2-expressing Tumors |  | 2020-10-06 | 2021-06-22 | 2021-06-09 | 2021-06-30 | 2021-06-30
37 | 20/LO/0417 | 268449 | A Prospective, Open-Label, Single-Arm, Phase 2, Multicenter Study Evaluating the Efficacy of Venetoclax Plus Ibrutinib in Subjects with T-Cell Prolymphocytic Leukemia | 2020-11-04 | 2018-12-14 | 2020-07-08 | 2020-06-01 | 2020-09-15 | 2020-09-18 | 2020-10-07 | Sponsor
38 | 20/LO/0478 | 275864 | A Modular, Multipart, Multi-arm, Open-label, Phase I/IIa Study to Evaluate the Safety and Tolerability of EP0042 Alone and in Combination with Anti-cancer Treatments in Patients with Advanced Malignancies | 2020-11-02 | 2020-03-02 | 2020-09-29 | 2020-07-29 | 2020-10-09 | 2020-10-16 | 2020-10-22
39 | 19/SC/0221 | 259880 | An open-label Phase I/IIa study to evaluate the safety and efficacy of CCS1477 as monotherapy in patients with advanced haematological malignancies. | 2021-06-14 | 2020-07-13 | 2020-07-27 | 2019-06-10 | 2021-05-18 | 2021-05-19 | 2021-05-20 | Sponsor
40 | 20/SC/0343 | 283482 | A Phase 1/2b, First-in-Human, Open-Label, Dose Escalation Study of Teclistamab, a Humanised BCMA x CD3 Bispecific Antibody, in Subjects with Relapsed or Refractory Multiple Myeloma. | 2021-01-05 | 2020-07-06 | 2020-11-16 | 2020-11-16 | 2020-12-18 | 2020-12-21 | 2020-12-22
41 | 19/NW/0700 | 268843 | A phase III trial of intensity-modulated proton beam therapy versus intensity modulated radiotherapy for multi-toxicity reduction in oropharyngeal cancer |  | 2020-02-21 | 2021-06-03 | 2019-12-12
42 | 19/SC/0514 | 268974 | Phase I, first in human trial evaluating BI 1387446 alone and in combination with BI 754091 in solid tumors. | 2020-12-17 | 2019-09-12 | 2020-08-19 | 2020-01-02 | 2020-08-25 | 2020-09-10 | 2020-10-21 | Neither
43 | 20/LO/0078 | 273839 | A Phase 2 Study in First Line Metastatic or Unresectable, Recurrent Head and Neck Squamous Cell Carcinoma to Evaluate Intratumoral MK-1454 in Combination with IV Pembrolizumab vs IV Pembrolizumab Monotherapy |  | 2019-12-23 | 2020-10-22 | 2020-03-30 | 2021-01-17 | 2021-01-29 | 2021-03-19 | NHS Provider
44 | 20/LO/0246 | 277170 | A Phase 3, randomized, placebo-controlled, double-blind clinical study of pembrolizumab (MK-3475) with or without lenvatinib (E7080/MK-7902) to evaluate the safety and efficacy of pembrolizumab and lenvatinib as 1L intervention in a PD-L1 selected population of participants with recurrent or metastatic head and neck squamous cell carcinoma (R/M HNSCC) (LEAP-010). | 2021-04-23 | 2020-01-13 | 2020-09-23 | 2020-05-04 | 2020-11-06 | 2020-11-12 | 2021-01-13 | Neither
45 | 19/YH/0079 | 259791 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study of Cabozantinib (XL184) in Subjects with Radioiodine-Refractory Differentiated Thyroid Cancer Who Have Progressed after Prior VEGFR-Targeted Therapy | 2020-11-23 | 2019-12-02 | 2020-09-09 | 2019-05-09 | 2020-10-22 | 2020-10-26 | 2020-11-09 | Neither
46 | 20/LO/0954 | 263351 | A Randomized, Double-Blind, Adaptive, Phase II/III Study of GSK3359609 in Combination with Pembrolizumab and 5FU-Platinum Chemotherapy versus Placebo in Combination with Pembrolizumab plus 5FU-Platinum Chemotherapy for First-Line Treatment of Recurrent/Metastatic Head and Neck Squamous Cell Carcinoma | 2020-12-14 | 2020-07-03 | 2020-11-17 | 2020-10-27 | 2020-12-09 | 2020-12-10 | 2020-12-11
47 | 20/WM/0056 | 271871 | A Multicentre, Randomized, Open-label, Phase 3 Trial Comparing LOXO-292 to Physicians Choice of Cabozantinib or Vandetanib in Patients with Progressive, Advanced, Kinase Inhibitor Naïve, RET-Mutant Medullary Thyroid Cancer | 2021-02-15 | 2020-03-05 | 2020-12-10 | 2020-04-08 | 2020-12-14 | 2020-12-14 | 2021-01-22
48 | 20/LO/0856 | 1003178 | A Phase 2, randomized, open-label three-arm clinical study to evaluate the safety and efficacy of lenvatinib (E7080/MK-7902) in combination with pembrolizumab (MK-3475) versus standard of care chemotherapy and lenvatinib monotherapy in participants with recurrent/metastatic head and neck squamous cell carcinoma (R/M HNSCC) that have progressed after platinum therapy and immunotherapy (PD-1/PD-L1 inhibitors) | 2021-03-31 | 2020-03-26 | 2020-08-13 | 2020-08-24 | 2021-01-07 | 2021-02-03 | 2021-03-02 | Sponsor
49 | 20/LO/1080 | 285427 | An Open-Label, Multicenter, Phase 1 Study of RP3 as a Single Agent and in Combination with PD1 Blockade in Patients with Solid Tumors |  | 2020-09-28 | 2021-05-07 | 2020-12-03 | 2021-05-19 | 2021-05-20 | 2021-05-20
50 | 20/EM/0245 | 284115 | A Phase 3 Randomized, Double-blind, Multicenter, Global Study of Monalizumab or Placebo in Combination With Cetuximab in Patients With Recurrent or Metastatic Squamous Cell Carcinoma of the Head and Neck Previously Treated With an Immune Checkpoint Inhibitor (INTERLINK-1) |  | 2020-07-31 | 2021-01-18 | 2020-12-18 | 2021-02-11 | 2021-02-18 | 2021-04-01 | Neither
51 | 19/LO/0200 | 224781 | MESO-PRIME: Pembrolizumab and Hypofractionated Stereotactic Radiotherapy in patients with Malignant Pleural Mesothelioma | 2021-04-13 | 2019-01-09 | 2021-02-01 | 2019-10-21 | 2021-03-17 | 2021-03-17 | 2021-04-08 | Sponsor
52 | 20/YH/0239 | 260910 | Remote monitoring of Wearable Activity Trackers for detection of TOXicity in people receiving systemic anticancer treatment: a feasibility study | 2020-12-18 | 2020-07-30 | 2020-10-16 | 2020-10-16 | 2020-12-03 | 2020-12-03 | 2020-12-03
53 | 20/LO/0019 | 263796 | A PHASE 1b, MULTICENTER, TWO-PART, OPENLABEL STUDY OF TRASTUZUMAB DERUXTECAN, AN ANTI-HUMAN EPIDERMAL GROWTH FACTOR RECEPTOR-2 (HER2)-ANTIBODY DRUG CONJUGATE (ADC), IN COMBINATION WITH PEMBROLIZUMAB, AN ANTI-PD-1 ANTIBODY, IN SUBJECTS WITH LOCALLY ADVANCED/METASTATIC BREAST OR NON-SMALL CELL LUNG CANCER (NSCLC) | 2020-11-13 | 2019-01-23 | 2020-08-12 | 2020-02-21 | 2020-09-11 | 2020-09-18 | 2020-10-12 | Neither
54 | 20/LO/0877 | 263065 | Improving Spinal Stereotactic Radiotherapy in difficult to treat cases | 2020-11-20 | 2020-06-03 | 2020-07-08 | 2020-07-08 | 2020-07-29 | 2020-07-29 | 2020-07-29 | Neither
55 | 18/LO/0122 | 238790 | A Phase III, Randomized, Double-blind Trial of Platinum Doublet Chemotherapy +/-Pembrolizumab (MK-3475) as Neoadjuvant/Adjuvant Therapy for Participants with Resectable Stage IIB or IIIA Non-small Cell Lung Cancer (NSCLC) (KEYNOTE-671) |  | 2019-07-05 | 2020-09-09 | 2018-04-30 | 2020-10-15 | 2020-10-21 | 2020-11-10 | Neither
56 | 20/LO/0452 | 278609 | A PHASE 2, MULTICENTER, OPEN-LABEL, MULTI-COHORT STUDY TO ASSESS SAFETY AND EFFICACY OF CC-90011 IN COMBINATION WITH NIVOLUMAB IN SUBJECTS WITH ADVANCED CANCERS | 2021-03-02 | 2019-12-15 | 2021-01-19 | 2020-05-27 | 2021-02-02 | 2021-02-05 | 2021-02-18
57 | 20/NE/0032 | 273692 | A PHASE III, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY OF ATEZOLIZUMAB PLUS CARBOPLATIN AND ETOPOSIDE WITH OR WITHOUT TIRAGOLUMAB (ANTI-TIGIT ANTIBODY) IN PATIENTS WITH UNTREATED EXTENSIVE-STAGE SMALL CELL LUNG CANCER |  | 2020-01-16 | 2020-08-26 | 2020-07-28 | 2020-08-27 | 2020-09-21 | 2020-10-03 | Neither
58 | 20/SW/0073 | 1003218 | A Phase 3 Study of Pembrolizumab (MK-3475) in Combination with Concurrent Chemoradiation Therapy Followed by Pembrolizumab with or without Olaparib vs Concurrent Chemoradiation Therapy Followed by Durvalumab in Participants with Unresectable, Locally Advanced, Stage III Non-Small Cell Lung Cancer (NSCLC) | 2021-03-02 | 2019-12-19 | 2020-12-09 | 2020-06-19 | 2021-02-03 | 2021-02-04 | 2021-02-23 | Neither
59 | LR/AG20/ES/0077 | 1003177 | A Randomized Phase 3 Study of Sitravatinib in Combination with Nivolumab Versus Docetaxel in Patients with Advanced Non-Squamous Non-Small Cell Lung Cancer with Disease Progression On or After Platinum-Based Chemotherapy and Checkpoint Inhibitor Therapy | 2021-06-15 | 2020-05-20 | 2021-03-31 | 2020-11-03 | 2021-04-21 | 2021-04-27 | 2021-05-13 | Neither
60 | 20/EM/0108 | 279150 | A Phase 3 Multicenter, Randomized, Open Label, Active-controlled, Study of AMG 510 Versus Docetaxel for the Treatment of Previously Treated Locally Advanced and Unresectable or Metastatic NSCLC Subjects With Mutated KRAS p.G12C |  | 2020-02-21 | 2020-09-16 | 2020-05-18 | 2021-02-09 | 2021-02-10 | 2021-02-15 | Sponsor
61 | 20/LO/1020 | 286291 | A Phase 3, Randomized Study of Amivantamab and Lazertinib Combination Therapy Versus Osimertinib Versus Lazertinib as First-Line Treatment in Patients with EGFR Mutated Locally Advanced or Metastatic Non-Small Cell Lung Cancer |  | 2020-08-21 | 2021-01-27 | 2020-10-22 | 2021-05-25 | 2021-05-25 | 2021-06-07 | Sponsor
62 | 20/NW/0260 | 1003209 | A Phase 3, Multicenter, Randomized, Double-blind, Placebo-Controlled Study of AG-881 in Subjects With Residual or Recurrent Grade 2 Glioma With an IDH1 or IDH2 Mutation |  | 2020-02-03 | 2020-07-27 | 2020-07-20 | 2021-03-08 | 2021-03-08 | 2021-03-26 | Both
63 | 20/LO/1200 | 278052 | BRCA-DIRECT: randomised evaluation in women diagnosed with breast cancer of digitally-delivered pre-test information for BRCA-testing |  | 2020-11-27 | 2021-05-20 | 2021-01-04 | 2021-07-03 | 2021-07-05
64 | 20/NE/0009 | 262268 | A Randomized Open-Label Phase 2 Study Evaluating Ramucirumab in Pediatric Patients and Young Adults with Relapsed Recurrent or Refractory Desmoplastic Small Round Cell Tumor |  | 2019-04-17 | 2020-12-09 | 2020-06-12 | 2020-12-14 | 2021-01-12 | 2021-02-22 | Neither
65 | 20/SC/0007 | 264068 | A PHASE I/II, MULTICENTER, OPEN-LABEL, MULTI-ARM STUDY EVALUATING THE SAFETY, TOLERABILITY, PHARMACOKINETICS, AND PRELIMINARY ACTIVITY OF IDASANUTLIN IN COMBINATION WITH EITHER CHEMOTHERAPY OR VENETOCLAX IN THE TREATMENT OF PEDIATRIC AND YOUNG ADULT PATIENTS WITH RELAPSED/REFRACTORY ACUTE LEUKEMIAS OR SOLID TUMORS | 2021-07-16 | 2019-05-17 | 2020-12-17 | 2020-02-21 | 2020-12-21 | 2020-12-21 | 2021-07-16 | Neither
66 | 20/EM/0082 | 264830 | An Open-Label, Single-Arm, Phase 1/2 Study Evaluating the Safety and Efficacy of Ponatinib for the Treatment of Recurrent or Refractory Leukemias or Solid Tumors in Pediatric Participants |  | 2019-04-17 | 2020-09-16 | 2020-06-22 | 2020-10-06 | 2020-10-13 | 2020-10-26 | Neither
67 | 19/WM/0143 | 254424 | An international multicenter phase II randomised trial evaluating and comparing two intensification treatment strategies for metastatic neuroblastoma patients with a poor response to induction chemotherapy | 2021-07-05 | 2019-07-29 | 2020-07-01 | 2020-01-08 | 2020-12-11 | 2020-12-16 | 2021-01-11 | Neither
68 | 20/LO/0081 | 269630 | An open label, multi-center roll-over study to assess long-term effect in pediatric patients treated with Tafinlar (dabrafenib) and/or Mekinist (trametinib) | 2020-12-04 | 2020-02-21 | 2020-09-15 | 2020-06-02 | 2020-11-11 | 2020-11-17 | 2020-11-19 | Sponsor
69 | 19/YH/0346 | 264517 | A Phase I, Open-label, Parallel Group Study to Investigate Olaparib Safety and Tolerability, Efficacy and Pharmacokinetics in Paediatric Patients with Solid Tumours |  | 2019-10-09 | 2021-04-08 | 2019-12-05 | 2021-04-09 | 2021-04-09 | 2021-04-14 | Neither
70 | 20/LO/1162 | 285291 | The HERMES trial: Hypofractionated Expedited Radiotherapy for Men with localisEd proState cancer. A phase II randomised study of ultrahypofractionated stereotactic body radiotherapy in men with localised prostate cancer. |  | 2020-03-11 | 2021-06-16 | 2021-01-12 | 2021-06-26 | 2021-06-29 |  | Sponsor
71 | 20/YH/0232 | 280105 | ATNEC–Axillary management in T1‐3N1M0 breast cancer patients with FNA or core biopsy proven nodal metastases at presentation who convert to node negative after NEoadjuvant Chemotherapy | 2021-02-26 | 2020-09-21 | 2020-09-28 | 2020-10-22 | 2020-12-11 | 2021-01-26 | 2021-02-02 | Nhs provider
72 | 19/NW/0705 | 257309 | The CAPER study: A Phase Ib clinical trial of Cyclophosphamide And PEmbrolizumab in metastatic Renal cell carcinoma (CAPER Trial) |  | 2019-11-18 | 2020-08-24 | 2020-01-14 | 2021-02-01 | 2021-02-04 | 2021-06-22 | Sponsor
73 | 20/NI/0131 | 278283 | A PHASE III, MULTICENTER, RANDOMIZED, OPEN-LABEL STUDY TO EVALUATE THE EFFICACY AND SAFETY OF ATEZOLIZUMAB GIVEN IN COMBINATION WITH CABOZANTINIB VERSUS CABOZANTINIB ALONE IN PATIENTS WITH INOPERABLE, LOCALLY ADVANCED, OR METASTATIC RENAL CELL CARCINOMA WHO EXPERIENCED RADIOGRAPHIC TUMOR PROGRESSION DURING OR AFTER IMMUNE CHECKPOINT INHIBITOR TREATMENT |  | 2020-04-22 | 2020-11-13 | 2020-10-21 | 2021-04-09 | 2021-04-09 | 2021-04-22 | Sponsor
74 | 20/NW/0216 | 279229 | A Randomized Phase II, Open label, Active controlled, Multicenter Study Investigating the Efficacy and Safety of UV1 Vaccination in Combination with Nivolumab and Ipilimumab as First line Treatment of Patients with Unresectable or Metastatic Melanoma (UV1-202) |  | 2020-11-06 | 2020-12-23 | 2020-07-13 | 2021-06-11 | 2021-06-15 | 2021-07-02 | Sponsor
75 | 20/LO/0351 | 277255 | A Phase III Study of AL3818 (Catequentinib, Anlotinib) Hydrochloride Monotherapy in Subjects with Metastatic or Advanced Alveolar Soft Part Sarcoma, Leiomyosarcoma and Synovial Sarcoma | 2020-11-26 | 2019-11-13 | 2020-09-30 | 2020-09-30 | 2020-10-29 | 2020-10-30 | 2020-11-11
76 | 11/LO/2024 | 285701 | A randomized phase III study of neoadjuvant chemotherapy followed by surgery versus surgery alone for patients with High Risk RetroPeritoneal Sarcoma |  | 2020-05-29 | 2020-12-16 | 2020-12-16 | 2020-12-16 | 2021-01-28 | 2021-04-12 | Sponsor
77 | 19/LO/1754 | 272127 | A Phase 3 Randomized, Double-Blind Study of Nivolumab or Placebo in Combination with Docetaxel, in Men with Metastatic Castration-resistant Prostate Cancer (CheckMate 7DX: CHECKpoint pathway and nivoluMAB clinical Trial Evaluation 7DX) | 2021-04-29 | 2019-11-29 | 2020-10-22 | 2019-11-26 | 2020-09-29 | 2020-10-23 | 2020-11-04 | Neither
78 | 21/LO/0178 | 287775 | A Phase II/III trial of Primary radiotherapy for Androgen sensitive Prostate cancer patients with Lymph nodes | 2021-06-24 | 2021-04-23 | 2021-04-23 | 2021-04-12 | 2021-06-18 | 2021-06-22 | 2021-06-24
79 | 19/LO/0712 | 257246 | IP4- CHRONOS: Comparative Health Research Outcomes of NOvel Surgery in Prostate Cancer |  | 2019-08-12 | 2020-07-01 | 2019-08-07 | 2020-09-29 | 2020-11-13 | 2020-11-16 | Nhs provider
80 | 19/EE/0348 | 261447 | A randomized phase II trial assessing trimodality therapy with or without adjuvant durvalumab (MEDI4736) to treat patients with muscle-invasive bladder cancer | 2021-02-23 | 2020-02-01 | 2020-10-12 | 2020-04-25 | 2021-01-08 | 2021-02-02 | 2021-02-10 | Nhs provider
81 | 20/EM/0209 | 286545 | A Phase 3 Randomized, Placebo-controlled, Double-blind Study of Niraparib in Combination with Abiraterone Acetate and Prednisone Versus Abiraterone Acetate and Prednisone for the Treatment of Participants with Deleterious Germline or Somatic Homologous Recombination Repair (HRR) Gene-Mutated Metastatic Castration-Sensitive Prostate Cancer (mCSPC) |  | 2020-08-11 | 2021-02-11 | 2020-10-13 | 2021-05-11 | 2021-05-19 | 2021-05-28 | Sponsor
82 | 20/SC/0337 | 281968 | A Phase III Double-Blind, Randomised, Placebo-Controlled Study Assessing the Efficacy and Safety of Capivasertib + Abiraterone Versus Placebo + Abiraterone as Treatment for Patients with De Novo Metastatic Hormone-Sensitive Prostate Cancer (mHSPC) Characterised by PTEN deficiency (CAPItello-281) | 2021-05-05 | 2020-07-10 | 2021-01-29 | 2020-12-08 | 2021-03-15 | 2021-03-16 | 2021-03-22 | Sponsor
83 | 21/NE/0025 | 247460 | PROCADE: A Multinational Phase 3, Randomized, Double-Blind, Non-inferiority, Efficacy and Safety Study of Oral HC-1119 versus Enzalutamide in Metastatic Castration-Resistant Prostate Cancer (mCRPC) |  | 2021-01-21 | 2021-01-21 | 2021-03-04 | 2021-06-22 | 2021-06-23 |  | Nhs provider