## 1.Data for upload Q3 PI
Record Number | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
1 | 21/NW/0035 | 1003512 | T-DM1 + Atezolizumab in high-risk HER2+ patients with residual disease after neoadjuvant taxane-based and HER2-targeted therapy |  | 2020-09-21 | 2021-04-06 | 2021-03-30 | 2021-11-10 | 2021-11-10 | 2021-11-22 | NHS provider
2 | 21/FT/0043 | 290151 | A Randomized Phase 3 Double-Blinded Study Comparing Efficacy of Niraparib to Placebo in Participants with either HER2-Negative BRCA-Mutated or Triple-negative Breast Cancer with Molecular Disease Based on Presence of Circulating Tumor DNA after Definitive Therapy |  | 2021-03-02 | 2021-05-11 | 2021-05-17 | 2021-09-07 | 2021-10-27 | 2021-11-26 | NHS provider
3 | 21/LO/0329 | 294195 | A Randomized, Open-Label, Phase 3 Trial of Tisotumab Vedotin vs Investigator’s Choice Chemotherapy in Second- or Third-Line Recurrent or Metastatic Cervical Cancer |  | 2021-03-01 | 2021-08-13 | 2021-06-23 | 2021-08-20 | 2021-08-27 | 2021-10-06 | Neither
4 | 21/SC/0164 | 1003547 | A Phase 3, Randomized, Double-Blind Study of Pembrolizumab versus Placebo in Combination With Adjuvant Chemotherapy With or Without Radiotherapy for the Treatment of Newly Diagnosed High-Risk Endometrial Cancer After Surgery With Curative Intent (KEYNOTE-B21 / ENGOT-en11 / GOG-3053). |  | 2021-01-04 | 2021-05-13 | 2021-06-14 | 2021-11-07 | 2021-11-09 |  | NHS provider
5 | 21/NW/0003 | 1003525 | A Phase II, Randomised, double-blind study of atezolizumab plus tiragolumab and atezolizumab plus placebo as first-line treatment in patients with recurrent/metastatic PD-L1 positive squamous cell carcinoma of the head and neck |  | 2021-01-12 | 2021-06-02 | 2021-02-17 | 2021-11-24 | 2021-11-24 | 2021-12-08 | Sponsor
6 | 19/LO/1743 | 241002 | A phase 1B of crizotinib either in combination or as single agent in pediatric patients with ALK, ROS1 or MET positive malignancies |  | 2017-07-01 | 2021-06-28 | 2021-06-25 | 2021-07-23 | 2021-08-02 | 2021-09-20 | Neither
7 | 19/LO/0546 | 250345 | Effectiveness and cost-effectiveness of inspiratory muscle training (IMT) for reducing postoperative pulmonary complications (PPC): a sham-controlled randomised controlled trial (RCT) (INSPIRE) | 2021-05-25 | 2020-01-13 | 2021-01-10 | 2019-05-16 | 2021-03-10 | 2021-04-29 | 2021-05-13 | Sponsor
8 | 21/HRA/0645 | 296247 | A Randomized, Observer-Blind, Placebo-Controlled, Phase 2/3 Study to Assess the Safety, Efficacy, and Immunogenicity of a Recombinant Coronavirus-Like Particle COVID-19 Vaccine in Adults 18 Years of Age or Older |  | 2021-02-10 | 2021-04-22 | 2021-04-07 | 2021-04-23 | 2021-04-26 |  | Sponsor
9 | 21/LO/0292 | 294693 | Hemithyroidectomy or Total-Thyroidectomy in 'low-risk' thyroid cancers |  | 2021-03-10 | 2021-10-27 | 2021-06-18 |  |  |  | Sponsor
10 | 19/EE/0369 | 257226 | A Phase III, multicentre,multinational randomised control trial investigating 1cm v 2cm wide excision margins for primary cutaneous melanoma. |  | 2021-06-23 | 2021-09-29 | 2020-06-04 |  |  |  | NHS provider
11 | 21/EM/0201 | 302236 | Immunogenicity and Safety of SARS-CoV-2 Recombinant Protein Vaccines with AS03 Adjuvant in Adults 18 Years of Age and Older as a Primary Series and Immunogenicity and Safety of a Booster Dose of SARS-CoV-2 Adjuvanted Recombinant Protein Vaccines (two Monovalent and one Bivalent) |  | 2021-07-20 | 2021-11-19 | 2021-09-01 | 2021-11-18 | 2021-11-24 | 2021-12-06
12 | 18/WM/0257 | 211232 | NOSTRA-Feasibility Study: A prospective non-randomised multi-centre feasibility study to assess if patients with residual cancer following dual-targeted neoadjuvant chemotherapy treatment for HER2-positive, ER-negative early breast cancer can be identified by multiple ultrasound-guided tumour bed core biopsies |  | 2021-08-05 | 2021-12-07 | 2019-02-11
13 | 21/YH/0162 | 297034 | Volatile vs Total intravenous Anaesthesia for major non-cardiac surgery: A pragmatic randomised triaL |  | 2021-06-02 | 2021-11-10 | 2021-09-30
14 | 20/NI/0128 | 273402 | A PHASE III, RANDOMISED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY AND SAFETY OF GDC-0077 PLUS PALBOCICLIB AND FULVESTRANT VERSUS PLACEBO PLUS PALBOCICLIB AND FULVESTRANT IN PATIENTS WITH PIK3CA-MUTANT, HORMONE RECEPTORPOSITIVE, HER2-NEGATIVE LOCALLY ADVANCED OR METASTATIC BREAST CANCER |  | 2019-10-24 | 2021-03-12 | 2020-11-27 | 2021-05-26 | 2021-06-08 | 2021-06-18 | NHS provider
15 | 20/LO/0963 | 281310 | Randomized, double-blind, phase 3 study of tucatinib or placebo in combination with ado-trastuzumab emtansine (T-DM1) for subjects with unresectable locally-advanced or metastatic HER2+ breast cancer. | 2021-04-26 | 2020-01-31 | 2021-03-05 | 2020-10-23 | 2021-03-03 | 2021-03-09 | 2021-03-26
16 | 19/NI/0126 | 254829 | SMALL: A Phase III, randomised, multi-centre trial addressing overtreatment of small screen-detected breast cancer by comparing standard surgery versus minimally invasive vacuum-assisted excision |  | 2019-09-15 | 2021-04-08 | 2019-10-15 | 2021-03-12 | 2021-04-26 | 2021-05-13 | Neither
17 | 20/LO/1114 | 1003435 | A PHASE III RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY EVALUATING THE EFFICACY AND SAFETY OF GDC-9545 COMBINED WITH PALBOCICLIB COMPARED WITH LETROZOLE COMBINED WITH PALBOCICLIB IN PATIENTS WITH ESTROGEN RECEPTOR-POSITIVE, HER2-NEGATIVE LOCALLY ADVANCED OR METASTATIC BREAST CANCER | 2021-07-16 | 2020-09-07 | 2021-06-08 | 2020-12-08 | 2021-06-03 | 2021-06-08 | 2021-06-14
18 | 21/FT/0019 | 293935 | eMonarcHER: A Randomized, Double Blind, Placebo-Controlled Phase 3 Study of Abemaciclib plus Standard Adjuvant Endocrine Therapy in Participants with High-Risk, Node-Positive, HR+, HER2+ Early Breast Cancer Who Have Completed Adjuvant HER2-Targeted Therapy |  | 2021-03-23 | 2021-07-08 | 2021-04-07 | 2021-09-30 | 2021-10-05 | 2021-10-15 | NHS provider
19 | 21/FT/0057 | 283571 | Roll Over StudY for Patients Who Have Completed a Previous Oncology Study with Olaparib and Are Judged by the Investigator to Clinically Benefit From Continued Treatment | 2021-09-08 | 2021-06-15 | 2021-08-03 | 2021-07-22 | 2021-09-02 | 2021-09-06 | 2021-09-08
20 | 20/LO/1200 | 278052 | BRCA-DIRECT: randomised evaluation in women diagnosed with breast cancer of digitally-delivered pre-test information for BRCA-testing | 2021-07-12 | 2020-11-27 | 2021-05-20 | 2021-01-04 | 2021-07-03 | 2021-07-05 | 2021-07-05
21 | 21/LO/0053 | 285061 | A Phase 1b Study Evaluating the Safety and Efficacy of AMG 160 in Combination With Enzalutamide in Subjects With Metastatic Castration- | 2021-09-17 | 2020-12-18 | 2021-05-24 | 2021-04-08 | 2021-06-16 | 2021-06-24 | 2021-07-13 | Sponsor
22 | 20/LO/0947 | 261727 | A multicenter, non-randomized, open-label phase 1b study to determine the maximum tolerated and recommended phase 2 dose of the ATR Inhibitor BAY 1895344 in combination with pembrolizumab and to characterize its safety, tolerability, pharmacokinetics and preliminary anti-tumour activity in patients with advanced solid tumours |  | 2020-07-14 | 2021-06-24 | 2020-09-30 | 2021-07-09 | 2021-07-12 | 2021-07-23 | Neither
23 | 20/LO/1287 | 279624 | A Phase 1 Open-Label, Dose Escalation and Expansion Trial to Investigate the Safety, Pharmacokinetics and Pharmacodynamics of CB307, a Trispecific Humabody T-cell Enhancer, in Patients with PSMA+ Advanced and/or Metastatic Solid Tumours (POTENTIA). | 2021-04-23 | 2020-12-04 | 2021-03-24 | 2021-02-01 | 2021-03-25 | 2021-03-29 | 2021-03-30
24 | 20/LO/1235 | 289189 | A Phase 1, Open-label, Dose-escalation Study of the PI3K Inhibitor SL-901 in Patients with Advanced Solid Tumors | 2021-03-19 | 2020-11-12 | 2021-01-06 | 2021-01-07 | 2021-03-01 | 2021-03-02 | 2021-03-18 | Sponsor
25 | 21/LO/0213 | 1003590 | ANV419 Single Agent (Parts A-C) or Combination (Part D) First in Human Study Phase 1/2: Open-label Dose Escalation and Expansion Study in Patients with Relapsed/Refractory Advanced Solid Tumors. | 2021-10-06 | 2021-04-26 | 2021-08-20 | 2021-05-13 | 2021-09-15 | 2021-09-17 | 2021-09-22
26 | 21/LO/0407 | 293694 | A Multicenter, Open-Label, Phase I Clinical Study to assess the Safety, Tolerability, Pharmacokinetics and Food-Effect of Inupadenant New Formulation in Participants with Advanced Solid Tumors | 2021-09-08 | 2021-05-13 | 2021-07-27 | 2021-07-27 | 2021-08-10 | 2021-08-12 | 2021-08-24
27 | 21/LO/0263 | 295239 | A Modular Phase I/IIa, Open-label, Multi-centre Study to Assess the Safety, Tolerability, Pharmacokinetics, Pharmacodynamics and Preliminary Efficacy of Ascending Doses of AZD5305 as Monotherapy and in Combination with Anti-cancer Agents in Patients with Advanced Solid Malignancies (PETRA) | 2021-09-29 | 2021-03-29 | 2021-05-27 | 2021-05-20 | 2021-07-15 | 2021-07-20 | 2021-07-27 | Sponsor
28 | 21/LO/0331 | 295691 | A Phase 1 Study of SGN-STNV in Advanced Solid Tumors | 2021-10-05 | 2021-04-07 | 2021-05-27 | 2021-05-19 | 2021-06-22 | 2021-06-30 | 2021-08-10 | neither
29 | 21/LO/0345 | 1003691 | A Phase 1a, Dose Escalation, Safety and Tolerability Study of NX-1607, a Casitas B-lineage lymphoma proto-oncogene (CBL-B) inhibitor, in Adults with Advanced Malignancies, with Phase 1b Expansion in Select Tumor Types | 2021-09-29 | 2021-06-07 | 2021-07-30 | 2021-07-22 | 2021-08-19 | 2021-08-25 | 2021-09-13
30 | 21/EE/0073 | 290147 | A Phase 1, Open Label, Dose-Escalation and Expansion Study to Evaluate the Safety, Pharmacokinetics and Initial Therapeutic Activity of AVA6000, a Novel FAP-activated Doxorubicin Prodrug Administered Intravenously in Patients with Locally Advanced or Metastatic Selected Solid Tumours | 2021-07-28 | 2021-04-28 | 2021-06-08 | 2021-05-25 | 2021-07-14 | 2021-07-16 | 2021-07-23
31 | 21/FT/0058 | 293068 | A Phase 1 Study Exploring the Safety, Tolerability, Pharmacokinetics, and Pharmacodynamics of INCB099318 in Participants With Select Advanced Solid Tumors | 2021-08-25 | 2021-04-26 | 2021-06-07 | 2021-05-17 | 2021-07-15 | 2021-07-15 | 2021-08-09 | neither
32 | 21/LO/0477 | 298897 | A Cancer Research UK Phase I/IIa open label, dose escalation and expansion trial of HMBD-001 (an anti-HER3 monoclonal antibody) given intravenously as a single agent and in combination in patients with advanced HER3 positive solid tumours. | 2021-11-10 | 2021-06-23 | 2021-08-19 | 2021-09-09 | 2021-10-07 | 2021-10-07 | 2021-10-15 | Sponsor
33 | 21/LO/0470 | 298938 | A Cancer Research UK Phase I/II, dose escalation and expansion trial of TT-702, a selective adenosine A2BR antagonist, given orally as a monotherapy agent and in combination, in patients with advanced solid tumours (CURATE) |  | 2021-07-22 | 2021-09-15 | 2021-09-08 | 2021-11-04 | 2021-11-08 | 2021-11-29 | Sponsor
34 | 21/LO/0806 | 305244 | A Phase 1 Clinical Study of NXP800 in Patients with Advanced Cancers |  | 2021-10-11 | 2021-11-17 | 2021-11-16 | 2021-12-10 | 2021-12-14
35 | 21/FT/0141 | 298127 | A Phase 1/2 Study Targeting Acquired Resistance Mechanisms in Patients with EGFR Mutant Non-Small Cell Lung Cancer |  | 2021-09-21 | 2021-11-15 | 2021-10-19
36 | 21/FT/0127 | 304627 | AN OPEN-LABEL, MULTICENTER, PHASE I STUDY TO EVALUATE SAFETY, PHARMACOKINETICS, AND PRELIMINARY ANTI-TUMOR ACTIVITY OF RO7444973 IN PARTICIPANTS WITH UNRESECTABLE AND/OR METASTATIC MAGE-A4-POSITIVE SOLID TUMORS |  | 2021-10-11 | 2021-11-26 | 2021-10-25 | 2021-12-17 | 2021-12-17
37 | 19/LO/1541 | 271255 | Open-Label Phase 2 Study of Ladiratuzumab Vedotin (LV) for Unresectable Locally Advanced or Metastatic Solid Tumors |  | 2019-07-30 | 2021-05-10 | 2019-11-29 | 2021-04-15 | 2021-05-20 | 2021-06-22 | Sponsor
38 | 18/SC/0583 | 238087 | A Phase 1 trial of the safety, tolerability and biological effects of intravenous Enadenotucirev, a novel oncolytic virus, in combination with chemoradiotherapy in locally advanced rectal cancer | 2021-11-22 | 2020-05-14 | 2021-03-12 | 2020-09-25 | 2021-04-23 | 2021-04-27 | 2021-09-13 | Sponsor
39 | 20/SC/0207 | 229134 | A Phase 1b/2 study of derazantinib as second-line monotherapy and combination therapy with paclitaxel, ramucirumab or atezolizumab in patients with HER2- negative gastric adenocarcinoma harboring FGFR genetic aberrations (FIDES-03) |  | 2020-11-06 | 2021-10-05 | 2020-07-09 | 2021-09-30 | 2021-10-07 | 2021-10-28 | Neither
40 | 20/EM/0160 | 282796 | A Global, Multicenter, Randomized, Placebocontrolled Phase 3 Trial To Compare The Efficacy And Safety Of Fruquintinib Plus Best Supportive Care To Placebo Plus Best Supportive Care In Patients With Refractory Metastatic Colon Cancer (Fresco-2) |  | 2020-06-11 | 2021-02-11 | 2021-02-11 | 2021-04-22 | 2021-05-14 | 2021-07-28 | Sponsor
41 | 20/LO/0995 | 286160 | A Phase 3 Global, Multicenter, Double-Blind Randomized Study of Carboplatin-Paclitaxel With INCMGA00012 or Placebo in Participants With Inoperable Locally Recurrent or Metastatic Squamous Cell Carcinoma of the Anal Canal Not Previously Treated With Systemic Chemotherapy (POD1UM-303/InterAACT 2) | 2021-01-15 | 2020-06-03 | 2021-01-06 | 2020-11-02 | 2021-01-07 | 2021-01-12 | 2021-01-15
42 | 20/SC/0326 | 286972 | A Randomized, Open-Label, Phase 3 Trial of Epcoritamab vs Investigator’s Choice Chemotherapy in Relapsed/Refractory Diffuse Large B-cell Lymphoma | 2021-06-29 | 2020-08-10 | 2021-01-29 | 2021-01-11 | 2021-02-24 | 2021-03-02 | 2021-04-26 | Neither
43 | 20/WS/0140 | 285076 | A Phase II single-arm study to investigate tepotinib combined with cetuximab in RAS/BRAF wild-type left-sided metastatic colorectal cancer (mCRC) patients having acquired resistance to anti-EGFR antibody targeting therapy due to MET amplification |  | 2020-06-16 | 2021-05-06 | 2020-09-25 | 2021-06-24 | 2021-06-24 | 2021-06-30 | Sponsor
44 | 20/SC/0365 | 1003436 | A Randomized, Double-blind, Placebo-controlled, Phase III Study of Neoadjuvant/Adjuvant Durvalumab and Standard Chemotherapy Followed by Adjuvant Durvalumab in Patients with Resectable Gastric and Gastroesophageal Cancer (GC/GEJC) | 2021-09-20 | 2020-11-09 | 2021-07-26 | 2020-11-13 | 2021-07-28 | 2021-07-29 | 2021-08-23
45 | 21/LO/0032 | 1003430 | A Phase 1/2b Multicenter, Open-label, Dose-escalation and Dose-expansion Study to Evaluate the Safety, Tolerability, Pharmacokinetics, Immunogenicity, and Antitumor Activity of Trastuzumab Deruxtecan (DS-8201a) Monotherapy and combinations in Adult Subjects with HER2 Overexpressing Gastric Cancer |  | 2020-12-02 | 2021-07-29 | 2021-02-09 | 2021-07-30 | 2021-08-10 | 2021-09-23 | Neither
46 | 21/YH/0024 | 1003543 | A Phase 3 Randomized Study of Lenvatinib in Combination with Pembrolizumab Versus Standard of Care in Participants with Metastatic Colorectal Cancer Who Have Received and Progressed On or After or Became Intolerant to Prior Treatment. | 2021-08-16 | 2021-02-01 | 2021-07-16 | 2021-03-25 | 2021-07-15 | 2021-07-20 | 2021-08-11
47 | 20/NW/0448 | 1003497 | A PHASE II, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY OF ATEZOLIZUMAB WITH OR WITHOUT BEVACIZUMAB IN COMBINATION WITH CISPLATIN + GEMCITABINE IN PATIENTS WITH UNTREATED, ADVANCED BILIARY TRACT CANCER | 2021-08-02 | 2021-01-18 | 2021-06-28 | 2021-02-01 | 2021-06-28 | 2021-06-29 | 2021-07-06
48 | 21/LO/0134 | 1003516 | A Phase 3, multicenter, randomized, double-blind, placebo-controlled trial comparing the efficacy and safety of tafasitamab plus lenalidomide in addition to R-CHOP versus R-CHOP in previously untreated, high-intermediate and high-risk patients with newly-diagnosed Diffuse Large B-Cell Lymphoma (DLBCL) | 2021-12-16 | 2021-03-22 | 2021-10-08 | 2021-03-22 | 2021-10-08 | 2021-10-11 | 2021-12-08
49 | 21/NW/0221 | 1003973 | A Phase 3 study of MK-4280A [co-formulated favezelimab (MK-4280) plus pembrolizumab (MK-3475)] Versus Standard of Care in Previously Treated Metastatic PDL1 positive Colorectal Cancer |  | 2021-07-21 | 2021-09-29 | 2021-10-07 | 2021-12-22 | 2021-12-23 | 2021-12-24 | Sponsor
50 |  | 302614 | A Phase IB/II Open-Label, Multicenter Study Evaluating The Safety, Efficacy, And Pharmacokinetics Of Mosunetuzumab In Combination With Tiragolumab With Or Without Atezolizumab In Patients With Relapsed Or Refractory B-Cell Non-Hodgkin Lymphoma |  | 2021-09-01 | 2021-11-02
51 | 21/LO/0033 | 1003213 | A Randomized, Phase 3, Double-Blind Study of Chemoradiotherapy With or Without Pembrolizumab for the Treatment of High-risk, Locally Advanced Cervical Cancer (KEYNOTE-A18 / ENGOT-cx11) | 2021-07-19 | 2020-02-14 | 2021-03-31 | 2021-03-30 | 2021-04-08 | 2021-04-16 | 2021-05-24 | Neither
52 | 21/NW/0097 | 1003662 | Phase 2 study of VS-6766 (dual RAF/MEK inhibitor) alone and in combination with defactinib (FAK inhibitor) in subjects with recurrent low grade serous ovarian cancer (LGSOC). | 2021-11-24 | 2021-04-01 | 2021-07-23 | 2021-06-04 | 2021-07-29 | 2021-08-10 | 2021-09-02 | Neither
53 | 21/NW/0116 | 1003450 | A Phase II, multicenter, open-label study to evaluate the efficacy and safety of Trastuzumab Deruxtecan (T-DXd, DS-8201a) for the treatment of selected HER2 Expressing Tumors. | 2021-08-03 | 2020-10-06 | 2021-06-22 | 2021-06-09 | 2021-06-30 | 2021-06-30 | 2021-07-19
54 | 21/NE/0148 | 295954 | A Phase 1b/2 Open-Label Study of the Efficacy and Safety of Etigilimab (MPH313) Administered in Combination with Nivolumab to Subjects with Locally Advanced or Metastatic Solid Tumors (ACTIVATE) | 2021-12-13 | 2021-05-05 | 2021-10-12 | 2021-10-01 | 2021-11-04 | 2021-11-09 | 2021-11-22
55 | 21/YH/0056 | 283442 | Prediction of Patient Drug Response Using an Ex Vivo Organ Culture (EVOC) on fresh human tumour samples from Metastatic Patients |  | 2021-05-06 | 2021-11-01 | 2021-04-08 | 2021-10-08
56 | 20/LO/1117 | 284930 | An open-label, phase 1/2, first in human study investigating the safety, tolerability, pharmacokinetics and efficacy of NVG-111 in subjects with relapsed/refractory chronic lymphocytic leukaemia and mantle cell lymphoma |  | 2020-09-14 | 2021-09-30 | 2020-10-30 | 2021-10-26 | 2021-10-27 |  | Sponsor
57 | 21/LO/0136 | 292014 | A Multi-arm Phase 1b Study of Teclistamab With Other Anticancer Therapies in Participants with Multiple Myeloma | 2021-12-16 | 2021-01-27 | 2021-10-21 | 2021-03-18 | 2021-12-07 | 2021-12-09 | 2021-12-09
58 | 21/SW/0020 | 292543 | An Open-Label, Multicenter, Non-Randomized Phase 2 Study of Pf 06863135 Monotherapy in Participants with Multiple Myeloma Who Are Refractory To At Least One Proteasome Inhibitor, One Immunomodulatory Drug and One Anti-Cd38 Antibody |  | 2021-02-04 | 2021-10-26 | 2021-05-06 | 2021-11-10 | 2021-11-24
59 | 20/EM/0223 | 285849 | A Randomized, Double-Blind, Phase 3 Study Evaluating the Safety and Efficacy of Venetoclax in Combination with Azacitidine in Patients Newly Diagnosed with Higher-Risk Myelodysplastic Syndrome (Higher-Risk MDS) | 2021-10-18 | 2021-03-08 | 2021-07-19 | 2020-10-21 | 2021-08-27 | 2021-09-03 | 2021-09-30 | Sponsor
60 | 21/NW/0061 | 295010 | A Phase 3 Open-Label, Randomized Study of LOXO-305 versus Investigator’s Choice of Idelalisib plus Rituximab or Bendamustine plus Rituximab in BTK Inhibitor Pretreated Chronic Lymphocytic Leukemia/Small Lymphocytic Lymphoma (BRUIN CLL321) |  | 2021-02-26 | 2021-08-13 |  |  |  |  | Both
61 | 21/LO/0346 | 1003339 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled, Multicenter Study of Ravulizumab in Adult and Adolescent Participants who have Thrombotic Microangiopathy (TMA) after Hematopoietic Stem Cell Transplant (HSCT) |  | 2021-05-25 | 2021-05-25 | 2021-06-25 |  |  |  | Sponsor
62 | 19/NW/0700 | 268843 | A phase III trial of intensity-modulated proton beam therapy versus intensity modulated radiotherapy for multi-toxicity reduction in oropharyngeal cancer |  | 2020-02-21 | 2021-06-03 | 2019-12-12 | 2021-07-09 | 2021-07-19 | 2021-08-09 | Sponsor
63 | 20/LO/1080 | 285427 | An Open-Label, Multicenter, Phase 1 Study of RP3 as a Single Agent and in Combination with PD1 Blockade in Patients with Solid Tumors | 2021-06-07 | 2020-09-28 | 2021-05-07 | 2020-12-03 | 2021-05-19 | 2021-05-20 | 2021-05-20
64 | 20/EM/0245 | 284115 | A Phase 3 Randomized, Double-blind, Multicenter, Global Study of Monalizumab or Placebo in Combination With Cetuximab in Patients With Recurrent or Metastatic Squamous Cell Carcinoma of the Head and Neck Previously Treated With an Immune Checkpoint Inhibitor. INTERLINK-1 | 2021-07-21 | 2020-07-31 | 2021-01-18 | 2020-12-18 | 2021-02-11 | 2021-02-18 | 2021-04-01 | Neither
65 | 20/LO/1285 | 285539 | A randomized, double-blind placebo-controlled, phase 3 study of Debio 1143 in combination with platinum-based chemotherapy and standard fractionation intensity modulated radiotherapy in patients with locally advanced squamous cell carcinoma of the head and neck, suitable for definitive chemoradiotherapy (TRILYNX). |  | 2020-06-06 | 2021-09-02 | 2021-02-09 | 2021-10-04 | 2021-10-05 | 2021-12-31 | Sponsor
66 | 21/FT/0017 | 290947 | A Phase II Study of cemiplimab, an anti-PD-1 monoclonal antibody, and ISA101b vaccine in patients with recurrent/metastatic HPV16- positive Oropharyngeal Cancer who have experienced disease progression with prior anti-PD-1 therapy |  | 2021-02-10 | 2021-09-07 | 2021-03-16 | 2021-10-05 | 2021-10-05 | 2021-10-21 | neither
67 | 20/SC/0357 | 279818 | A First-in-Human Study of CDK-002 (exoSTING) in Subjects with Advanced/Metastatic, Recurrent, Injectable Solid Tumours, with Emphasis on Squamous Cell Carcinoma of the Head and Neck, Triple Negative Breast Cancer, Anaplastic Thyroid Carcinoma, and Cutaneous Squamous Cell Carcinoma |  | 2020-10-01 | 2021-06-16 | 2021-02-12 | 2021-12-23 | 2021-12-24 | 2021-12-29 | Sponsor
68 | 21/EM/0046 | 293505 | A phase 2 study of ALX148 in combination with pembrolizumab in patients with advanced head and neck squamous cell carcinoma |  | 2021-04-27 | 2021-11-03 | 2021-08-17 | 2021-11-10 | 2021-11-17
69 | 19/LO/0200 | 224781 | MESO-PRIME: Pembrolizumab and Hypofractionated Stereotactic Radiotherapy in patients with Malignant Pleural Mesothelioma | 2021-04-13 | 2019-01-09 | 2021-02-01 | 2019-10-21 | 2021-03-17 | 2021-03-17 | 2021-04-08 | Sponsor
70 | 20/LO/0452 | 278609 | A PHASE 2, MULTICENTER, OPEN-LABEL, MULTI-COHORT STUDY TO ASSESS SAFETY AND EFFICACY OF CC-90011 IN COMBINATION WITH NIVOLUMAB IN SUBJECTS WITH ADVANCED CANCERS | 2021-03-02 | 2019-12-15 | 2021-01-19 | 2020-05-27 | 2021-02-02 | 2021-02-05 | 2021-02-18
71 | 20/ES/0077 | 1003177 | A Randomized Phase 3 Study of Sitravatinib in Combination with Nivolumab Versus Docetaxel in Patients with Advanced Non-Squamous Non-Small Cell Lung Cancer with Disease Progression On or After Platinum-Based Chemotherapy and Checkpoint Inhibitor Therapy | 2021-06-15 | 2020-05-20 | 2021-03-31 | 2020-11-03 | 2021-04-21 | 2021-04-27 | 2021-05-13 | Neither
72 | 20/NE/0198 | 278450 | A Phase 1/2 Trial of the Synthetic Cannabinoid ART27.13 in Patients with Cancer Anorexia and Weight Loss | 2021-11-29 | 2020-08-17 | 2021-08-27 | 2020-12-15 | 2021-09-07 | 2021-09-14 | 2021-10-21 | neither
73 | 20/LO/1020 | 286291 | A Phase 3, Randomized Study of Amivantamab and Lazertinib Combination Therapy Versus Osimertinib Versus Lazertinib as First-Line Treatment in Patients with EGFR Mutated Locally Advanced or Metastatic Non-Small Cell Lung Cancer |  | 2020-08-21 | 2021-01-27 | 2020-10-22 | 2021-05-25 | 2021-05-25 | 2021-06-07 | Sponsor
74 | 20/LO/1180 | 288253 | A Randomized, Open-label Phase 3 Study of Combination Amivantamab and Carboplatin-Pemetrexed Therapy, Compared with Carboplatin-Pemetrexed, in Patients with EGFR Exon 20ins-mutated Locally Advanced or Metastatic Non-Small Cell Lung Cancer |  | 2020-10-13 | 2021-10-20 | 2021-01-04 | 2021-11-18 | 2021-11-19 | 2022-01-11 | NHS Provider
75 | 20/LO/1141 | 279274 | A Phase III, Randomized, Multicenter, Double-blind, Placebo-controlled Study to Determine the Efficacy of Adjuvant Durvalumab in Combination with Platinum-based Chemotherapy in Completely Resected Stage II-III NSCLC (MeRmaiD-1) |  | 2020-09-28 | 2021-09-15 | 2021-01-29 |  |  |  | Sponsor
76 | 21/LO/0461 | 294283 | HERTHENA-Lung01: A Phase 2 Randomized Open-Label Study of Patritumab Deruxtecan (U3-1402) in Subjects with Previously Treated Metastatic or Locally Advanced EGFR-mutated Non-Small Cell Lung Cancer(NSCLC) |  | 2021-06-04 | 2021-09-20 | 2021-07-13 | 2021-10-27 | 2021-10-28 | 2021-11-10 | NHS Provider
77 | 19/YH/0346 | 264517 | A Phase I, Open-label, Parallel Group Study to Investigate Olaparib Safety and Tolerability, Efficacy and Pharmacokinetics in Paediatric Patients with Solid Tumours |  | 2019-10-09 | 2021-04-08 | 2019-12-05 | 2021-04-09 | 2021-04-09 | 2021-04-14 | Neither
78 | 20/LO/1054 | 1003358 | A Pivotal Phase 1/2, Single-Arm, Open-label Study to Evaluate the Safety and Efficacy of Ponatinib With Chemotherapy in Pediatric Patients With Philadelphia Chromosome-Positive (Ph+) Acute Lymphoblastic Leukemia (ALL) Who Have Relapsed or Are Resistant or Intolerant to a Prior Tyrosine Kinase Inhibitor-Containing Therapy, or Who Have the T315I Mutation |  | 2020-06-01 | 2021-04-13 | 2020-12-07 | 2021-10-20 | 2021-10-21 |  | Sponsor
79 | 19/LO/1336 | 256748 | An International Prospective Trial on High-Risk Medulloblastoma in Patients Older than 3 Years |  | 2020-06-30 | 2021-09-30 | 2019-11-13 |  |  |  | Neither
80 | 20/NE/0269 | 284657 | High-Risk Neuroblastoma Study 2 of SIOP-Europa-Neuroblastoma (SIOPEN) |  | 2020-12-09 | 2021-11-19 | 2021-01-19 | 2021-12-14 | 2021-12-16
81 | 20/WM/0328 | 285958 | A Phase II, Open-label, Study to Assess the Efficacy, Safety, and Tolerability of AZD4635 in Combination with Durvalumab and in Combination with Cabazitaxel and Durvalumab in Patients Who Have Progressive Metastatic Castrate-Resistant Prostate Cancer (AARDVARC) |  | 2020-06-11 | 2021-07-05 | 2021-04-07 | 2021-07-06 | 2021-07-07 |  | Sponsor
82 | 21/FT/0066 | 294138 | PSMAfore: A phase III, Open-label, Multi-Center, Randomized Study Comparing 177Lu-PSMA-617 vs. a Change of androgen receptor-directed therapy in the Treatment of Taxane Naïve Men with Progressive Metastatic Castrate Resistant Prostate Cancer |  | 2021-01-20 | 2021-07-20 | 2021-06-30 | 2021-09-14 | 2021-09-14 | 2021-09-21 | Sponsor
83 | 21/SC/0293 | 301065 | Dose escalation study to evaluate the safety, tolerability, and anti-tumor activity of single agent IMU-935 in patients with progressive, metastatic castration resistant prostate cancer | 2021-12-09 | 2021-10-08 | 2021-11-10 | 2021-10-26 | 2021-11-19 | 2021-11-19 | 2021-11-26
84 | 20/LO/1162 | 285291 | The HERMES trial: Hypofractionated Expedited Radiotherapy for Men with localisEd proState cancer. A phase II randomised study of ultrahypofractionated stereotactic body radiotherapy in men with localised prostate cancer. | 2021-07-28 | 2020-03-11 | 2021-01-12 | 2021-01-12 | 2021-06-26 | 2021-06-29 | 2021-07-27 | Sponsor
85 | 19/SC/0086 | 249778 | A Phase 2, Open-label, 3-Cohort, Multicenter Study of Autologous Tumor Infiltrating Lymphocytes LN 144/LN-145 as a Single-Therapy, or in Combination with Pembrolizumab, to Treat Solid Tumors in Patients with Metastatic Melanoma, Head and Neck Squamous Cell Carcinoma, and Non-Small-Cell Lung Cancer |  | 2019-10-17 | 2021-10-13 | 2019-06-06 | 2021-10-08 | 2021-10-15 |  | Neither
86 | 20/YH/0147 | 276888 | Pan Tumor Study for Long Term Follow-up of Cancer Survivors Who Have Participated in Trials Investigating Nivolumab | 2021-10-07 | 2020-04-15 | 2021-07-14 | 2020-07-17 | 2021-07-12 | 2021-07-16 | 2021-09-21 | Neither
87 | 19/NW/0046 | 227794 | A parallel arm, biomarker driven, phase II feasibility trial to determine the role of circulating tumour DNA in guiding a switch between targeted therapy and immune therapy in patients with advanced cutaneous melanoma |  | 2020-06-03 | 2021-07-14 | 2019-03-26 | 2021-07-08 | 2021-09-06 | 2021-09-09 | Sponsor
88 | 19/NE/0321 | 264778 | Master Protocol to Assess the Safety and Antitumor Activity of Genetically Engineered NY-ESO-1-Specific (c259) T Cells, alone or in combination with other agents, in HLA-A2+ Participants with NY-ESO-1 and/or LAGE-1a Positive Solid Tumors | 2021-11-01 | 2020-09-23 | 2021-08-16 | 2020-01-24 | 2021-08-23 | 2021-08-27 | 2021-09-03 | neither
89 | 21/SC/0053 | 287444 | A Phase I, Open-label Multi-dose Two-Part Study to Characterize the Effects of a Strong CYP3A4 Inhibitor on the Steady-State Pharmacokinetics of Tazemetostat (EPZ-6438), and the Effects of a Strong CYP3A4 Inducer on the Steady-State Pharmacokinetics of Tazemetostat in Subjects with Advanced Malignancies |  | 2020-05-12 | 2021-07-15 | 2021-06-04 | 2021-08-23 | 2021-08-25 |  | Sponsor
90 | 21/SW/0038 | 1003680 | A Phase 2/3, Randomized, Multicenter Study to Evaluate AL102 in Patients with Progressing Desmoid Tumors | 2021-10-07 | 2021-03-19 | 2021-08-06 | 2021-05-13 | 2021-08-04 | 2021-08-10 | 2021-08-31
91 | 18/NI/0203 | 248385 | An Open-label, Crossover Study of the Effect of Food on the Pharmacokinetics of Paclitaxel Administered Orally as Oraxol |  | 2021-03-29 | 2021-11-10 | 2019-01-16 | 2021-12-07 | 2021-12-09
92 | 21/FT/0113 | 300747 | A Randomized Multicenter Phase 3 Study of Milademetan Versus Trabectedin in Patients with Dedifferentiated Liposarcoma | 2021-12-30 | 2021-08-27 | 2021-11-09 | 2021-10-11 | 2021-12-07 | 2021-12-09 | 2021-12-17
93 | 21/EE/0180 | 293884 | Stereotactic body radiotherapy in addition to standard of care treatment in patients with rare oligometastatic cancers (OligoRARE): a randomized, phase 3, open-label trial. |  | 2021-07-14 | 2021-07-14 | 2022-01-10 |  |  |  | Sponsor
94 | 21/LO/0150 | 280335 | A Randomised phase II trial of Enhancement of efficacy of Atezolizumab by Radiotherapy in Metastatic urothelial carcinoma |  | 2021-02-05 | 2021-05-14 | 2021-03-09 | 2021-07-14 | 2021-07-30 | 2021-09-15 | Sponsor
95 | 19/NE/0174 | 264235 | A first-in-human, dose titration and expansion trial to evaluate safety, immunogenicity and preliminary efficacy of W_pro1 in patients with metastatic castration resistant prostate cancer and W_pro1 in combination with cemiplimab and/or goserelin acetate in patients with high-risk, localized prostate cancer |  | 2019-09-11 | 2021-06-28 | 2019-07-24 | 2021-08-25 | 2021-09-15 | 2022-01-14 | NHS Provider
96 | 21/LO/0178 | 287775 | A Phase II/III trial of Primary radiotherapy for Androgen sensitive Prostate cancer patients with Lymph nodes | 2021-06-24 | 2021-04-23 | 2021-04-23 | 2021-04-12 | 2021-06-18 | 2021-06-22 | 2021-06-24
97 | 20/EM/0209 | 286545 | A Phase 3 Randomized, Placebo-controlled, Double-blind Study of Niraparib in Combination with Abiraterone Acetate and Prednisone Versus Abiraterone Acetate and Prednisone for the Treatment of Participants with Deleterious Germline or Somatic Homologous Recombination Repair (HRR) Gene-Mutated Metastatic Castration-Sensitive Prostate Cancer (mCSPC) |  | 2020-08-11 | 2021-02-11 | 2020-10-13 | 2021-05-11 | 2021-05-19 | 2021-05-28 | Sponsor
98 | 20/SC/0337 | 281968 | A Phase III Double-Blind, Randomised, Placebo-Controlled Study Assessing the Efficacy and Safety of Capivasertib + Abiraterone Versus Placebo + Abiraterone as Treatment for Patients with De Novo Metastatic Hormone-Sensitive Prostate Cancer (mHSPC) Characterised by PTEN deficiency (CAPItello-281) | 2021-05-05 | 2020-07-10 | 2021-01-29 | 2020-12-08 | 2021-03-15 | 2021-03-16 | 2021-03-22 | Sponsor
99 | 21/NE/0025 | 247460 | PROCADE: A Multinational Phase 3, Randomized, Double-Blind, Non-inferiority, Efficacy and Safety Study of Oral HC-1119 versus Enzalutamide in Metastatic Castration-Resistant Prostate Cancer (mCRPC) |  | 2021-01-21 | 2021-05-13 | 2021-03-04 | 2021-06-22 | 2021-06-23 | 2021-09-15 | Nhs provider
100 | 21/YH/0049 | 1003548 | A PHASE III, DOUBLE-BLIND, MULTICENTER, RANDOMIZED STUDY OF ATEZOLIZUMAB (ANTI-PD L1 ANTIBODY) VERSUS PLACEBO AS ADJUVANT THERAPY IN PATIENTS WITH HIGH RISK MUSCLE INVASIVE BLADDER CANCER WHO ARE CTDNA-POSITIVE FOLLOWING CYSTECTOMY | 2021-12-13 | 2020-12-18 | 2021-06-28 | 2021-05-07 | 2021-09-10 | 2021-09-10 | 2021-09-15 | Sponsor
101 | 18/NW/0432 | 239796 | Safety and pharmacokinetics of ODM-208 in patients with metastatic castration-resistant prostate cancer |  | 2021-03-29 | 2021-07-19 | 2018-09-03 | 2021-08-25 | 2021-08-25 | 2021-09-20 | Neither
102 | 21/NW/0074 | 294508 | Phase 3 study investigating the efficacy and safety of TAVT-45 (abiraterone acetate) Granules for Oral Suspension (a novel abiraterone acetate formulation) relative to a reference abiraterone acetate formulation in patients with metastatic Castrate Sensitive Prostate Cancer (mCSPC) and metastatic Castrate Resistant Prostate Cancer (mCRPC) | 2021-12-29 | 2021-05-13 | 2021-09-01 | 2021-05-04 | 2021-10-04 | 2021-10-12 | 2021-10-25 | neither
103 | 21/LO/0509 | 295209 | A Dose Regimen-Finding Study to Evaluate the Safety, Tolerability, Pharmacokinetics, and Activity of Oradoxel Monotherapy in Subjects with Advanced Malignancies, delivered in a Modular Format. |  | 2021-04-19 | 2021-08-24 | 2021-08-23 | 2021-10-12 | 2021-10-13 | 2021-11-02 | Neither
104 | 21/EM/0158 | 297323 | TALAPRO-3: A Phase 3, Randomized, Double-Blind, Study Of Talazoparib With Enzalutamide Versus Placebo With Enzalutamide In Men With DDR Gene Mutated Metastatic Castration-Sensitive Prostate Cancer |  | 2021-04-09 | 2021-07-23 | 2021-08-13 | 2021-11-19 | 2021-11-19 | 2022-01-10 | NHS Provider