## Q1 22-23
| Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Comments | Reasons for delay correspond to:
1 | 21/NI/0071 | 1003467 | A Phase 3, Randomized, Open-label Study to Evaluate the Safety and Efficacy of Pembrolizumab plus Lenvatinib plus Chemotherapy Induction Therapy Followed by Pembrolizumab plus Lenvatinib Compared with Chemotherapy in Participants with Previously Untreated Advanced/Metastatic HER2 Negative Gastric/Gastroesophageal Junction Adenocarcinoma |  | 2020-10-19 | 2022-02-03 | 2021-06-04 | 2022-06-08 | 2022-06-06 |  | 2022-06-28 | Both
2 | 20/EE/0254 | 283893 | An Open-Label, Multicenter, Randomized Phase 3 Study of First-Line Encorafenib Plus Cetuximab with or without Chemotherapy Versus Standard of Care Therapy with a Safety Lead-In of Encorafenib and Cetuximab Plus Chemotherapy in Participants with Metastatic BRAF V600E-Mutant Colorectal Cancer |  | 2021-01-12 | 2022-03-16 | 2021-01-20 |  |  |  |  | Both
3 | 18/NE/0256 | 237779 | Identification of genetic factors that predispose to immune checkpoint inhibitor toxicity | 2022-04-13 | 2021-07-16 | 2022-02-15 | 2018-08-13 | 2022-03-01 | 2022-03-03 |  | 2022-03-29
4 | 21/EM/0201 | 302236 | Immunogenicity and Safety of SARS-CoV-2 Recombinant Protein Vaccines with AS03 Adjuvant in Adults 18 Years of Age and Older as a Primary Series and Immunogenicity and Safety of a Booster Dose of SARS-CoV-2 Adjuvanted Recombinant Protein Vaccines (two Monovalent and one Bivalent) | 2021-12-07 | 2021-07-20 | 2021-11-19 | 2021-09-01 | 2021-11-18 | 2021-11-24 |  | 2021-12-06
5 |  | 1004764 | An adaptive clinical trial of AZD7442 and SARS-CoV-2 vaccination in immunosuppressed patients highly vulnerable to infection with SARS-CoV-2 virus. |  | 2022-06-10 | 2022-06-10
6 | 21/LO/0292 | 294693 | Hemithyroidectomy or Total-Thyroidectomy in 'low-risk' thyroid cancers | 2022-06-17 | 2021-03-10 | 2021-07-21 | 2021-06-18 | 2022-01-18 | 2022-01-19 |  | 2022-02-25 | Both
7 | 20/NW/0230 | 278525 | Phase 3, Multinational, Randomized, Open-Label, Three Parallel-Arm Study of PF-06801591, an anti-PD-1 antibody, in Combination with Bacillus Calmette- Guerin (BCG Induction With or Without BCG Maintenance) Versus BCG (Induction and Maintenance) in Participants with High-Risk, BCG Naïve Non-Muscle Invasive Bladder Cancer |  | 2021-01-21 | 2022-05-17 | 2020-06-18 | 2022-05-19 | 2022-06-22
8 | 21/YH/0162 | 297034 | Volatile vs Total intravenous Anaesthesia for major non-cardiac surgery: A pragmatic randomised triaL | 2022-01-06 | 2021-06-02 | 2021-11-10 | 2021-09-30 | 2021-12-16 | 2021-12-21 |  | 2022-01-05
9 | 18/WM/0257 | 211232 | NOSTRA-Feasibility Study: A prospective non-randomised multi-centre feasibility study to assess if patients with residual cancer following dual-targeted neoadjuvant chemotherapy treatment for HER2-positive, ER-negative early breast cancer can be identified by multiple ultrasound-guided tumour bed core biopsies |  | 2021-08-05 | 2021-12-07 | 2019-02-11 | 2022-05-10 | 2022-06-01 |  |  | Sponsor
10 | 19/EE/0369 | 257226 | A Phase III, multicentre,multinational randomised control trial investigating 1cm v 2cm wide excision margins for primary cutaneous melanoma. |  | 2021-06-23 | 2021-09-29 | 2020-06-04 | 2022-04-08 | 2022-05-03 |  | 2022-05-30 | NHS Provider
11 | 21/FT/0097 | 286505 | A randomised trial of early detection of molecular relapse with circulating tumour DNA tracking and treatment with palbociclib plus fulvestrant versus standard endocrine therapy in patients with ER positive HER2 negative breast cancer |  | 2021-09-28 | 2022-03-07 | 2021-09-14 | 2022-03-17 | 2022-03-17 |  | 2022-03-18 | Neither
12 | 21/FT/0019 | 293935 | eMonarcHER: A Randomized, Double Blind, Placebo-Controlled Phase 3 Study of Abemaciclib plus Standard Adjuvant Endocrine Therapy in Participants with High-Risk, Node-Positive, HR+, HER2+ Early Breast Cancer Who Have Completed Adjuvant HER2-Targeted Therapy |  | 2021-03-23 | 2021-07-08 | 2021-04-07 | 2021-09-30 | 2021-10-05 |  | 2021-10-15 | NHS Provider
13 | 21/FT/0057 | 283571 | Roll Over StudY for Patients Who Have Completed a Previous Oncology Study with Olaparib and Are Judged by the Investigator to Clinically Benefit From Continued Treatment | 2021-09-08 | 2021-06-15 | 2021-08-03 | 2021-07-22 | 2021-09-02 | 2021-09-06 |  | 2021-09-08
14 | 21/FT/0098 | 1003884 | SERENA-6: A Phase III, Double-blind, Randomised Study to Assess Switching to AZD9833 (a Next Generation, Oral SERD) + CDK4/6 Inhibitors (Palbociclib or Abemaciclib) vs Continuing NSAI + CDK4/6 Inhibitors in HR+/HER2- MBC Patients with Detectable ESR1 Mutation Without Clinical or Radiological Progression During 1L Treatment with NSAI + CDK4/6 Inhibitor A ctDNA Guided Early Switch Study |  | 2021-09-20 | 2022-01-25 | 2021-09-14 | 2022-01-26 | 2022-01-28 |  | 2022-02-14 | Neither
15 | 21/FT/0006 | 292412 | A Phase 2 Basket Study of Tucatinib in Combination with Trastuzumab in Subjects with Previously Treated, Locally-Advanced Unresectable or Metastatic Solid Tumors Driven by HER2 Alterations | 2022-05-11 | 2021-06-26 | 2022-04-04 | 2021-04-06 | 2022-04-22 | 2022-04-26 |  | 2022-05-06
16 | 21/LO/0625 | 1004050 | A Phase 3, Open-label, Randomized Study of Dato-DXd Versus Investigator’s Choice of Chemotherapy in Participants With Inoperable or Metastatic Hormone Receptor‑Positive / HER2‑Negative Breast Cancer Who Have Been Treated With One or Two Prior Lines of Systemic Chemotherapy |  | 2022-01-11 | 2022-06-20 | 2021-12-01
17 | 19/SC/0086 | 249778 | A Phase 2, Open-label, 3-Cohort, Multicenter Study of Autologous Tumor Infiltrating Lymphocytes LN 144/LN-145 as a Single-Therapy, or in Combination with Pembrolizumab, to Treat Solid Tumors in Patients with Metastatic Melanoma, Head and Neck Squamous Cell Carcinoma, and Non-Small-Cell Lung Cancer |  | 2019-10-17 | 2021-10-13 | 2019-06-06 | 2021-10-08 | 2021-10-15 |  | 2022-06-06 | Sponsor
18 | 19/NE/0321 | 264778 | Master Protocol to Assess the Safety and Antitumor Activity of Genetically Engineered NY-ESO-1-Specific (c259) T Cells, alone or in combination with other agents, in HLA-A2+ Participants with NY-ESO-1 and/or LAGE-1a Positive Solid Tumors | 2021-11-01 | 2020-09-23 | 2021-08-16 | 2020-01-24 | 2021-08-23 | 2021-08-27 |  | 2021-09-03 | Neither
19 | 21/SS/0054 | 300133 | A Phase 3 Randomized Study Comparing Bortezomib, Lenalidomide and Dexamethasone (VRd) followed by Ciltacabtagene Autoleucel, a Chimeric Antigen Receptor T cell (CAR-T) Therapy Directed Against BCMA versus Bortezomib, Lenalidomide, and Dexamethasone (VRd) followed by Lenalidomide and Dexamethasone (Rd) Therapy in Participants with Newly Diagnosed Multiple Myeloma for Whom Hematopoietic Stem Cell Transplant is Not Planned as Initial Therapy |  | 2021-07-21 | 2021-11-30 | 2021-09-02 | 2022-05-06 | 2022-05-06 |  |  | NHS Provider
20 | 21/LO/0753 | 280601 | ASTEROID: A Phase I trial of ASTX660 in combination with Pembrolizumab in patients with solid tumours: utilizing triple IAP blockade as a strategy to maximize Immunogenic cell Death and the generation of an efficient adaptive immune response | 2022-03-02 | 2021-10-04 | 2021-11-19 | 2021-11-19 | 2022-01-28 | 2022-02-09 |  | 2022-02-28 | Sponsor
21 | 21/FT/0126 | 291322 | A Phase 1b Study Evaluating the Safety, Tolerability, Pharmacokinetics and Efficacy of Delta-like Protein 3 Half-life Extended Bispecific T-cell Engager AMG 757 in Subjects with De Novo or Treatment Emergent Neuroendocrine Prostate Cancer |  | 2021-09-17 | 2022-01-06 | 2021-12-21 | 2022-02-14 | 2022-02-16 |  | 2022-02-21 | Sponsor
22 | 21/LO/0213 | 1003590 | ANV419 Single Agent (Parts A-C) or Combination (Part D) First in Human Study Phase 1/2: Open-label Dose Escalation and Expansion Study in Patients with Relapsed/Refractory Advanced Solid Tumours. | 2021-10-06 | 2021-04-26 | 2021-08-20 | 2021-05-13 | 2021-09-15 | 2021-09-17 |  | 2021-09-22
23 | 21/LO/0407 | 293694 | A Multicenter, Open-Label, Phase I Clinical Study to assess the Safety, Tolerability, Pharmacokinetics and Food-Effect of Inupadenant New Formulation in Participants with Advanced Solid Tumors | 2021-09-08 | 2021-05-13 | 2021-07-27 | 2021-07-27 | 2021-08-10 | 2021-08-12 |  | 2021-08-24
24 | 21/LO/0345 | 1003691 | A Phase 1a, Dose Escalation, Safety and Tolerability Study of NX-1607, a Casitas B-lineage lymphoma proto-oncogene (CBL-B) inhibitor, in Adults with Advanced Malignancies, with Phase 1b Expansion in Select Tumor Types | 2021-09-29 | 2021-06-07 | 2021-07-30 | 2021-07-22 | 2021-08-19 | 2021-08-25 |  | 2021-09-13
25 | 21/LO/0477 | 298897 | A Cancer Research UK Phase I/IIa open label, dose escalation and expansion trial of HMBD-001 (an anti-HER3 monoclonal antibody) given intravenously as a single agent and in combination in patients with advanced HER3 positive solid tumours. | 2021-11-10 | 2021-06-23 | 2021-08-19 | 2021-09-09 | 2021-10-07 | 2021-10-07 |  | 2021-10-15 | Sponsor
26 | 21/LO/0470 | 298938 | A Cancer Research UK Phase I/II, dose escalation and expansion trial of TT-702, a selective adenosine A2BR antagonist, given orally as a monotherapy agent and in combination, in patients with advanced solid tumours (CURATE) | 2022-01-05 | 2021-07-22 | 2021-09-15 | 2021-09-08 | 2021-11-04 | 2021-11-08 |  | 2021-11-29 | Sponsor
27 | 21/LO/0806 | 305244 | A Phase 1 Clinical Study of NXP800 in Patients with Advanced Cancers | 2022-01-07 | 2021-10-11 | 2021-11-17 | 2021-11-16 | 2021-12-10 | 2021-12-14 |  | 2021-12-22
28 | 21/FT/0141 | 298127 | A Phase 1/2 Study Targeting Acquired Resistance Mechanisms in Patients with EGFR Mutant Non-Small Cell Lung Cancer | 2022-03-16 | 2021-09-21 | 2021-11-15 | 2021-10-19 | 2022-01-17 | 2022-01-21 |  | 2022-02-08 | Sponsor
29 | 21/FT/0127 | 304627 | AN OPEN-LABEL, MULTICENTER, PHASE I STUDY TO EVALUATE SAFETY, PHARMACOKINETICS, AND PRELIMINARY ANTI-TUMOR ACTIVITY OF RO7444973 IN PARTICIPANTS WITH UNRESECTABLE AND/OR METASTATIC MAGE-A4-POSITIVE SOLID TUMORS | 2022-04-27 | 2021-10-11 | 2021-11-26 | 2021-10-25 | 2021-12-17 | 2021-12-17 |  | 2021-12-20 | Neither
30 | 21/LO/0687 | 1003783 | A Phase 1/2a Open Label, Multicenter Study to Assess the Safety, Tolerability, Pharmacokinetics and Efficacy of AFM24 in combination with Atezolizumab in Patients with selected Advanced/Metastatic EGFR expressing Cancers |  | 2021-09-28 | 2022-02-11 | 2021-11-18 | 2022-03-04 | 2022-03-04 |  | 2022-03-23 | Neither
31 | 21/FT/0154 | 305655 | A first-in-human dose-escalation and expansion trial with the antibody-drug conjugate BYON3521 to evaluate the safety, pharmacokinetics and efficacy in patients with c-MET expressing locally advanced or metastatic solid tumours. |  | 2021-10-08 | 2022-02-16 | 2021-11-28 | 2022-03-09 | 2022-03-15 |  | 2022-04-20 | Sponsor
32 | 22/WS/0004 | 304351 | Phase 1/2 Study of the Safety, Pharmacokinetics, and Preliminary Clinical Activity of BT7480 in Patients With Nectin-4 Associated Advanced Malignancies |  | 2021-12-16 | 2022-06-21 | 2022-04-13
33 | 20/SC/0207 | 229134 | A Phase 1b/2 study of derazantinib as second-line monotherapy and combination therapy with paclitaxel, ramucirumab or atezolizumab in patients with HER2- negative gastric adenocarcinoma harboring FGFR genetic aberrations (FIDES-03) |  | 2020-11-06 | 2021-10-05 | 2020-07-09 | 2021-09-30 | 2021-10-07 |  | 2021-10-28 | Sponsor
34 | 20/SC/0365 | 1003436 | A Randomized, Double-blind, Placebo-controlled, Phase III Study of Neoadjuvant/Adjuvant Durvalumab and Standard Chemotherapy Followed by Adjuvant Durvalumab in Patients with Resectable Gastric and Gastroesophageal Cancer (GC/GEJC) | 2021-09-20 | 2020-11-09 | 2021-07-26 | 2020-11-13 | 2021-07-28 | 2021-07-29 |  | 2021-08-23
35 | 20/SS/0122 | 286331 | A Randomized, Double-blind, Placebo-Controlled, Active-Comparator, Multicenter, Phase 3 Study of Brentuximab Vedotin or Placebo in Combination With Lenalidomide and Rituximab in Subjects with Relapsed or Refractory Diffuse Large B-cell Lymphoma (DLBCL) |  | 2020-11-05 | 2022-02-21 | 2021-05-13 | 2022-02-18 | 2022-02-22 |  | 2022-03-04 | Neither
36 | 21/LO/0032 | 1003430 | A Phase 1/2b Multicenter, Open-label, Dose-escalation and Dose-expansion Study to Evaluate the Safety, Tolerability, Pharmacokinetics, Immunogenicity, and Antitumor Activity of Trastuzumab Deruxtecan (DS-8201a) Monotherapy and combinations in Adult Subjects with HER2 Overexpressing Gastric Cancer |  | 2020-12-02 | 2021-07-29 | 2021-02-09 | 2021-07-30 | 2021-08-10 |  | 2021-09-23 | Neither
37 | 21/YH/0024 | 1003543 | A Phase 3 Randomized Study of Lenvatinib in Combination with Pembrolizumab Versus Standard of Care in Participants with Metastatic Colorectal Cancer Who Have Received and Progressed Through or Became Intolerant to Prior Treatment | 2021-08-16 | 2021-02-01 | 2021-07-16 | 2021-03-25 | 2021-07-15 | 2021-07-20 |  | 2021-08-11
38 | 21/EM/0109 | 295535 | A Phase 3, Multicenter, 2-Arm Randomized, Open-Label Study of Trastuzumab Deruxtecan in Subjects with HER2 Positive Metastatic and/or Unresectable Gastric or Gastro Esophageal Junction (GEJ) Adenocarcinoma Subjects who have Progressed on or After a Trastuzumab-Containing Regimen (DESTINY-Gastric04) |  | 2021-02-08 | 2022-04-20 | 2021-08-03 | 2022-05-17 | 2022-05-24 |  | 2022-05-31 | Neither
39 | 21/LO/0134 | 1003516 | A Phase 3, multicenter, randomized, double-blind, placebo-controlled trial comparing the efficacy and safety of tafasitamab plus lenalidomide in addition to R-CHOP versus R-CHOP in previously untreated, high-intermediate and high-risk patients with newly-diagnosed Diffuse Large B-Cell Lymphoma (DLBCL) | 2021-12-16 | 2021-03-22 | 2021-10-08 | 2021-03-22 | 2021-10-08 | 2021-10-11 |  | 2021-12-08
40 | 21/WS/0036 | 1003558 | A Phase 3, Randomized, Open-Label, Controlled, Multicenter Study of Zandelisib (ME-401) in Combination with Rituximab Versus Standard Immunochemotherapy in Patients with Relapsed Indolent Non-Hodgkin’s Lymphoma (iNHL) – The COASTAL Study |  | 2021-02-18 | 2021-12-15 | 2021-05-11 | 2022-02-25 | 2022-02-28 |  | 2022-04-07 | NHS Provider
41 | 21/SC/0151 | 295726 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled, Multicenter Study to Evaluate the Efficacy and Safety of Tafasitamab Plus Lenalidomide in Addition to Rituximab Versus Lenalidomide in Addition to Rituximab in Patients With Relapsed/Refractory (R/R) Follicular Lymphoma Grade 1 to 3a or R/R Marginal Zone Lymphoma. |  | 2021-04-27 | 2022-04-26 | 2021-07-09 | 2022-05-11 | 2022-05-12
42 | 21/WA/0033 | 292503 | AA Multi-arm, Phase II, Open-Label, Multicentre Study to Assess the Preliminary Efficacy of RXC004 in Monotherapy and in Combination with Nivolumab, in Patients with Ring Finger Protein 43 (RNF43) or R-spondin (RSPO) Aberrated, Metastatic, Microsatellite Stable, Colorectal Cancer who have Progressed following Therapy with Current Standard of Care |  | 2021-03-03 | 2022-05-31 | 2021-02-23
43 | 21/NW/0221 | 1003973 | A Phase 3 study of MK-4280A [co-formulated favezelimab (MK-4280) plus pembrolizumab (MK-3475)] Versus Standard of Care in Previously Treated Metastatic PDL1 positive Colorectal Cancer | 2021-12-29 | 2021-07-21 | 2021-09-29 | 2021-10-07 | 2021-12-22 | 2021-12-23 |  | 2021-12-24 | Sponsor
44 | 21/WS/0108 | 302614 | A Phase IB/II Open-Label, Multicenter Study Evaluating The Safety, Efficacy, And Pharmacokinetics Of Mosunetuzumab In Combination With Tiragolumab With Or Without Atezolizumab In Patients With Relapsed Or Refractory B-Cell Non-Hodgkin Lymphoma |  | 2021-09-01 | 2022-06-13 | 2021-10-18 | 2022-06-27 | 2022-06-27
45 | 21/WA/0232 | 1003955 | A Phase 3, Randomized, Open-Label Study to Evaluate the Efficacy and Safety of Pembrolizumab (MK3475) + Lenvatinib (E7080/MK-7902) with Chemotherapy-Induction Followed by Pembrolizumab + Lenvatinib Compared with Chemotherapy as First-line Intervention in Participants with Metastatic Esophageal Carcinoma. |  | 2021-09-20 | 2022-02-01 | 2021-09-16 | 2022-06-14 | 2022-06-22 |  |  | Sponsor
46 | 21/FT/0128 | 303399 | A randomized, double-blind, phase III study comparing NIS793 in combination with gemcitabine and nab-paclitaxel versus placebo combined with gemcitabine and nab-paclitaxel for first line treatment of metastatic pancreatic ductal adenocarcinoma (mPDAC) |  | 2021-11-15 | 2022-05-20 | 2021-12-13 | 2022-06-20 | 2022-06-21 |  | 2022-06-24
47 | 20/LO/1158 | 273531 | A Phase 1b/2, First-in-Human, Dose Escalation and Expansion Study of XMT-1536 In Patients with Solid Tumors Likely to Express NaPi2b | 2022-04-28 | 2020-06-25 | 2021-12-14 | 2020-12-17 | 2022-01-12 | 2022-01-14 |  | 2022-04-15 | NHS Provider
48 | 21/NW/0097 | 1003662 | Phase 2 study of VS-6766 (dual RAF/MEK inhibitor) alone and in combination with defactinib (FAK inhibitor) in subjects with recurrent low grade serous ovarian cancer (LGSOC). | 2021-11-24 | 2021-04-01 | 2021-07-23 | 2021-06-04 | 2021-07-29 | 2021-08-10 |  | 2021-09-02 | Neither
49 | 21/LO/0329 | 294195 | A Randomized, Open-Label, Phase 3 Trial of Tisotumab Vedotin vs Investigator’s Choice Chemotherapy in Second- or Third-Line Recurrent or Metastatic Cervical Cancer | 2021-12-14 | 2021-03-01 | 2021-08-13 | 2021-06-23 | 2021-08-20 | 2021-08-27 |  | 2021-10-06 | Neither
50 | 21/NE/0148 | 295954 | A Phase 1b/2 Open-Label Study of the Efficacy and Safety of Etigilimab (MPH313) Administered in Combination with Nivolumab to Subjects with Locally Advanced or Metastatic Solid Tumors | 2021-12-13 | 2021-05-05 | 2021-10-12 | 2021-10-01 | 2021-11-04 | 2021-11-09 |  | 2021-11-22
51 | 21/YH/0056 | 283442 | Prediction of Patient Drug Response Using an Ex Vivo Organ Culture (EVOC) on fresh human tumour samples from Metastatic Patients | 2022-04-04 | 2021-05-06 | 2021-11-01 | 2021-04-08 | 2021-10-08 | 2022-01-18 |  | 2022-02-03 | NHS Provider
52 | 21/NE/0188 | 304025 | A Phase 1/2a/3 Evaluation of the Safety and Efficacy of Adding AL3818, a Dual Receptor Tyrosine Kinase, Inhibitor, to Standard Platinum-Based Chemotherapy in Subjects with Recurrent or Metastatic, Endometrial, Ovarian, Fallopian, Primary Peritoneal or Cervical Carcinoma | 2022-05-24 | 2021-07-23 | 2022-04-08 | 2021-12-09 | 2022-04-14 | 2022-04-21 |  | 2022-05-11
53 | 21/LO/0842 | 1004268 | A Phase 3, Randomized, Double-Blind, Adaptive, Placebo/Paclitaxel-Controlled Study of AVB-S6-500 in Combination with Paclitaxel in Patients with Platinum-Resistant Recurrent Ovarian Cancer (AXLerate-OC) | 2022-07-07 | 2022-01-19 | 2022-04-08 | 2021-12-23 | 2022-04-11 | 2022-04-11 |  | 2022-05-18 | NHS Provider
54 | 20/LO/1117 | 284930 | An open-label, phase 1/2, first in human study investigating the safety, tolerability, pharmacokinetics and efficacy of NVG-111 in subjects with relapsed/refractory chronic lymphocytic leukaemia and mantle cell lymphoma | 2022-04-13 | 2020-09-14 | 2021-09-30 | 2020-10-30 | 2021-10-26 | 2021-10-27 |  | 2022-03-07 | Sponsor
55 | 21/LO/0136 | 292014 | A Multi-arm Phase 1b Study of Teclistamab With Other Anticancer Therapies in Participants with Multiple Myeloma | 2021-12-16 | 2021-01-27 | 2021-10-21 | 2021-03-18 | 2021-12-07 | 2021-12-09 |  | 2021-12-09
56 | 21/SW/0020 | 292543 | An Open-Label, Multicenter, Non-Randomized Phase 2 Study of Pf 06863135 Monotherapy in Participants with Multiple Myeloma Who Are Refractory To At Least One Proteasome Inhibitor, One Immunomodulatory Drug and One Anti-Cd38 Antibody |  | 2021-02-04 | 2021-10-26 | 2021-05-06 | 2021-11-10 | 2021-11-24 |  |  | Sponsor
57 | 21/LO/0063 | 288284 | A Phase 1 Multidose Study to Evaluate the Safety and Tolerability of XmAb®13676 in Patients with CD20-Expressing Hematologic Malignancies |  | 2021-01-11 | 2021-11-10 | 2021-03-10 | 2021-12-14 | 2022-01-21 |  | 2022-02-21 | NHS Provider
58 | 20/EM/0223 | 285849 | A Randomized, Double-Blind, Phase 3 Study Evaluating the Safety and Efficacy of Venetoclax in Combination with Azacitidine in Patients Newly Diagnosed with Higher-Risk Myelodysplastic Syndrome (Higher-Risk MDS) | 2021-10-18 | 2021-03-08 | 2021-07-19 | 2020-10-21 | 2021-08-27 | 2021-09-03 |  | 2021-09-30 | Sponsor
59 | 21/EM/0123 | 292892 | AGAVE-201, A Phase 2, Open-label, Randomized, Multicenter Study to Evaluate the Efficacy, Safety and Tolerability of Axatilimab at 3 Different Doses in Patients with Recurrent or Refractory Active Chronic Graft Versus Host Disease who have Received at least 2 Lines of Systemic Therapy | 2022-07-11 | 2021-05-21 | 2022-04-06 | 2021-07-14 | 2022-05-10 | 2022-05-11 |  |  | neither
60 | 21/NW/0061 | 295010 | A Phase 3 Open-Label, Randomized Study of LOXO-305 versus Investigator’s Choice of Idelalisib plus Rituximab or Bendamustine plus Rituximab in BTK Inhibitor Pretreated Chronic Lymphocytic Leukemia/Small Lymphocytic Lymphoma (BRUIN CLL321) | 2022-05-25 | 2021-04-19 | 2021-08-13 | 2021-04-16 | 2022-03-29 | 2022-04-07 |  | 2022-05-16 | Both
61 |  | 1003339 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled, Multicenter Study of Ravulizumab in Adult and Adolescent Participants who have Thrombotic Microangiopathy (TMA) after Hematopoietic Stem Cell Transplant (HSCT) |  | 2021-05-25 | 2022-05-03 | 2021-06-25 |  |  |  |  | Sponsor
62 | 21/SC/0059 | 289212 | An Open-Label, Multicenter, Phase 1b/2 Study of the Safety and Efficacy of KRT-232 in Combination with Acalabrutinib in Subjects with Relapsed/Refractory Diffuse Large B-cell Lymphoma or Relapsed/Refractory Chronic Lymphocytic Leukemia |  | 2021-03-11 | 2022-05-05 | 2021-07-02 | 2022-05-09 | 2022-05-24 |  | 2022-06-08
63 | 21/SS/0065 | 299954 | A Phase 3 Randomized Study Comparing Teclistamab in Combination with Daratumumab SC (Tec-Dara) versus Daratumumab SC, Pomalidomide, and Dexamethasone (DPd) or Daratumumab SC, Bortezomib, and Dexamethasone (DVd) in Participants with Relapsed or Refractory Multiple Myeloma | 2022-04-28 | 2021-07-05 | 2021-12-02 | 2021-10-12 | 2022-03-24 | 2022-03-30 |  | 2022-04-13 | NHS Provider
64 | 21/SS/0007 | 292045 | A Phase III, Multicenter, Open-Label, Randomized Study to Evaluate the Efficacy and Safety of Belantamab Mafodotin in Combination with Pomalidomide and Dexamethasone (B-Pd) versus Pomalidomide plus Bortezomib and Dexamethasone (PVd) in Participants with Relapsed/Refractory Multiple Myeloma (DREAMM 8) |  | 2021-01-13 | 2022-06-29 | 2021-03-29 | 2022-06-28 | 2022-07-01
65 | 20/LO/0238 | 265114 | Risk-Adapted therapy Directed According to Response comparing treatment escalation and de-escalation strategies in newly diagnosed patients with multiple myeloma (NDMM) suitable for stem cell transplant (TE). |  | 2021-10-29 | 2022-04-08 | 2020-05-15 |  |  |  |  | Both
66 | 21/WA/0221 | 1003867 | A PHASE 1/2, OPEN-LABEL, MULTICENTER STUDY TO EVALUATE A DOSING REGIMEN WITH TWO STEP-UP PRIMING DOSES AND LONGER DOSING INTERVALS OF ELRANATAMAB (PF-06863135) MONOTHERAPY IN PARTICIPANTS WITH RELAPSED/REFRACTORY MULTIPLE MYELOMA | 2022-02-01 | 2021-12-01 | 2021-12-03 | 2021-08-13 | 2022-01-20 | 2022-01-21 |  | 2022-02-01
67 | 21/NW/0266 | 1003963 | A Phase 2 Study to Evaluate the Efficacy and Safety of MK-1026 in Participants with Hematologic Malignancies |  | 2021-04-23 | 2022-02-14 | 2021-10-21 |  | 2022-07-12 |  |  | NHS Provider
68 |  | 1003756 | A PHASE 3, RANDOMIZED, MULTICENTER, OPEN-LABEL STUDY COMPARING IBERDOMIDE, DARATUMUMAB AND DEXAMETHASONE (IberDd) VERSUS DARATUMUMAB, BORTEZOMIB, AND DEXAMETHASONE (DVd) IN SUBJECTS WITH RELAPSED OR REFRACTORY MULTIPLE MYELOMA (RRMM) (EXCALIBER-RRMM) |  | 2022-02-09 | 2022-06-23
69 | 21/SC/0356 | 1004077 | A Phase 1, Dose Escalation, and Cohort Expansion Study Evaluating NX-5948, a Bruton’s Tyrosine Kinase (BTK) Degrader, in Adults with Relapsed/Refractory B-cell Malignancies |  | 2022-01-12 | 2022-05-05
70 | 20/LO/1285 | 285539 | A randomized, double-blind placebo-controlled, phase 3 study of Debio 1143 in combination with platinum-based chemotherapy and standard fractionation intensity modulated radiotherapy in patients with locally advanced squamous cell carcinoma of the head and neck, suitable for definitive chemoradiotherapy (TRILYNX). | 2022-03-28 | 2020-06-06 | 2021-09-02 | 2021-02-09 | 2021-10-04 | 2021-10-05 |  | 2021-12-31 | Sponsor
71 | 21/NE/0006 | 1003337 | An open-label, phase I/II study of TSP-Y058-739, a genetically-modified strain of the bacterium Yersinia enterocolitica, in patients with advanced solid tumours |  | 2020-08-10 | 2022-05-30 | 2021-03-01 | 2022-06-16 | 2022-06-17 |  | 2022-07-05
72 | 20/SC/0425 | 290504 | A multicentre, open-label, non-randomized, phase Ib, neoadjuvant study of intravenous dosing of NG-641, an oncolytic adenoviral vector expressing a fibroblast activation protein-directed bi-specific T-cell activator antibody fragment (FAP-TAc) and an immune enhancer module (CXCL9/CXCL10/interferon alpha2), as monotherapy or in combination with pembrolizumab in patients with surgically resectable squamous cell carcinoma of the head and neck (Mode Of Action Transgene study- MOAT) | 2022-06-01 | 2020-11-23 | 2022-02-02 | 2021-02-10 | 2022-04-11 | 2022-04-11 |  | 2022-04-14 | NHS Provider
73 | 21/FT/0017 | 290947 | A Phase II Study of cemiplimab, an anti-PD-1 monoclonal antibody, and ISA101b vaccine in patients with recurrent/metastatic HPV16- positive Oropharyngeal Cancer who have experienced disease progression with prior anti-PD-1 therapy |  | 2021-02-10 | 2021-09-07 | 2021-03-16 | 2021-10-05 | 2021-10-05 |  | 2021-10-21 | Neither
74 | 20/SC/0357 | 279818 | A First-in-Human Study of CDK-002 (exoSTING) in Subjects with Advanced/Metastatic, Recurrent, Injectable Solid Tumours, with Emphasis on Squamous Cell Carcinoma of the Head and Neck, Triple Negative Breast Cancer, Anaplastic Thyroid Carcinoma, and Cutaneous Squamous Cell Carcinoma | 2022-01-06 | 2020-10-01 | 2021-07-27 | 2021-02-12 | 2021-12-23 | 2021-12-24 |  | 2021-12-29 | Sponsor
75 | 21/EM/0046 | 293505 | A phase 2 study of ALX148 in combination with pembrolizumab in patients with advanced head and neck squamous cell carcinoma | 2022-01-06 | 2021-04-27 | 2021-11-03 | 2021-08-17 | 2021-11-10 | 2021-11-17 |  | 2021-12-21
76 | 21/SC/0058 | 293504 | A phase 2 study of ALX148 in combination with pembrolizumab and chemotherapy in patients with advanced head and neck squamous cell carcinoma (ASPEN-04) | 2022-04-11 | 2021-04-27 | 2022-01-12 | 2021-08-17 | 2022-03-10 | 2022-03-21 |  | 2022-03-31 | NHS Provider
77 | 20/SC/0319 | 277083 | Accelerating the Development and implementation of Personalised Treatments of DNA Damage Response agents and radiotherapy +/- immunotherapy for head and neck squamous cell cancer |  | 2021-02-03 | 2022-02-16 | 2020-10-15 | 2022-03-25 | 2022-04-12 |  | 2022-06-08 | Sponsor
78 | 21/EE/0068 | 295731 | The BURAN Study of Buparlisib (AN2025) In Combination with Paclitaxel Compared to Paclitaxel Alone, in Patients with Recurrent or Metastatic Head and Neck Squamous Cell Carcinoma | 2022-03-14 | 2021-06-07 | 2022-01-19 | 2021-09-20 | 2022-01-21 | 2022-01-25 |  | 2022-03-07
79 |  | 1004779 | A Phase 2 Study of Magrolimab Combination Therapy in Patients with Head and Neck Squamous Cell Carcinoma |  | 2022-05-16 | 2022-05-26
80 | 21/WS/0171 | 302709 | PARABLE: Proton beam therapy in patients with breast cancer: evaluating early and late effects |  | 2022-02-07 | 2022-02-07 | 2022-02-22 | 2022-04-06 | 2022-04-06 |  | 2022-06-21 | Sponsor
81 | 20/LO/0223 | 274833 | A Randomized, Open-Label, Phase 3 Study of Pralsetinib versus Standard of Care for First Line Treatment of RET fusion-positive, Metastatic Non-Small Cell Lung Cancer | 2022-02-01 | 2019-12-03 | 2022-01-14 | 2020-06-11 | 2022-01-26 | 2022-01-27 |  | 2022-01-28
82 | 20/LO/0070 | 273315 | A Randomized Phase 3 Multicenter Open-label Study to Compare the Efficacy of TAK-788 as First-line Treatment Versus Platinum-Based Chemotherapy in Patients With Non–Small Cell Lung Cancer With EGFR Exon 20 Insertion Mutations |  | 2020-01-08 | 2022-03-13 | 2020-08-07 | 2022-04-22 | 2022-04-26 |  | 2022-05-16 | Neither
83 | 20/NE/0198 | 278450 | A Phase 1/2 Trial of the Synthetic Cannabinoid ART27.13 in Patients with Cancer Anorexia and Weight Loss | 2021-11-29 | 2020-08-17 | 2021-08-27 | 2020-12-15 | 2021-09-07 | 2021-09-14 |  | 2021-10-21 | Neither
84 | 20/LO/1180 | 288253 | A Randomized, Open-label Phase 3 Study of Combination Amivantamab and Carboplatin-Pemetrexed Therapy, Compared with Carboplatin-Pemetrexed, in Patients with EGFR Exon 20ins-mutated Locally Advanced or Metastatic Non-Small Cell Lung Cancer | 2022-01-27 | 2020-10-13 | 2021-10-20 | 2021-01-04 | 2021-11-18 | 2021-11-19 |  | 2022-01-11 | NHS Provider
85 | 20/LO/1141 | 279274 | A Phase III, Randomized, Multicenter, Double-blind, Placebo-controlled Study to Determine the Efficacy of Adjuvant Durvalumab in Combination with Platinum-based Chemotherapy in Completely Resected Stage II-III NSCLC (MeRmaiD-1) |  | 2020-09-28 | 2021-09-15 | 2021-01-29 | 2022-01-20 | 2022-01-21 |  | 2022-03-08 | Sponsor
86 | 21/LO/0461 | 294283 | HERTHENA-Lung01: A Phase 2 Randomized Open-Label Study of Patritumab Deruxtecan (U3-1402) in Subjects with Previously Treated Metastatic or Locally Advanced EGFR-mutated Non-Small Cell Lung Cancer(NSCLC) |  | 2021-06-04 | 2021-09-20 | 2021-07-13 | 2021-10-27 | 2021-10-28 |  | 2021-11-10 | NHS Provider
87 | 22/NW/0037 | 1004165 | A randomised open-label phase III trial of Reduced Frequency pembrolizumab immuNothErapy for first-line treatment of patients with advanced non-small cell lung cancer (NSCLC) utilising a novel multi-arm frequency-response optimisation design |  | 2022-02-10 | 2022-05-18 | 2022-03-09 | 2022-05-27 | 2022-06-29 |  | 2022-07-01
88 | 22/EM/0050 | 1004984 | A Phase 2, Open-Label, Single-Arm, Multicenter Study to Evaluate the Efficacy and Safety of Pemigatinib in Participants With Previously Treated Glioblastoma or Other Primary Central Nervous System Tumors Harboring Activating FGFR1-3 Alterations (FIGHT-209) |  | 2022-03-04 | 2022-05-05 | 2022-04-07 |  |  |  |  | Sponsor
89 | 19/LO/1336 | 256748 | An International Prospective Trial on High-Risk Medulloblastoma in Patients Older than 3 Years |  | 2020-06-30 | 2021-12-02 | 2019-11-13 |  |  |  |  | Neither
90 | 20/NE/0269 | 284657 | High-Risk Neuroblastoma Study 2 of SIOP-Europa-Neuroblastoma (SIOPEN) | 2022-03-04 | 2020-12-09 | 2021-11-19 | 2021-01-19 | 2021-12-14 | 2021-12-16 |  | 2022-03-03 | Sponsor
91 | 20/WM/0328 | 285958 | A Phase II, Open-label, Study to Assess the Efficacy, Safety, and Tolerability of AZD4635 in Combination with Durvalumab and in Combination with Cabazitaxel and Durvalumab in Patients Who Have Progressive Metastatic Castrate-Resistant Prostate Cancer (AARDVARC) |  | 2020-06-11 | 2021-07-05 | 2021-04-07 | 2021-07-06 | 2021-07-07 |  |  | Sponsor
92 | 21/FT/0066 | 294138 | PSMAfore: A phase III, Open-label, Multi-Center, Randomized Study Comparing 177Lu-PSMA-617 vs. a Change of androgen receptor-directed therapy in the Treatment of Taxane Naïve Men with Progressive Metastatic Castrate Resistant Prostate Cancer | 2022-01-07 | 2021-01-20 | 2021-07-20 | 2021-06-30 | 2021-09-14 | 2021-09-14 |  | 2021-09-21 | Sponsor
93 | 20/LO/0886 | 1003064 | A Phase 3, Randomized, Open-Label, Controlled Study of Cabozantinib (XL184) in Combination with Atezolizumab vs Second Novel Hormonal Therapy (NHT) in Subjects with High-Risk, Metastatic Castration-Resistant Prostate Cancer |  | 2021-03-11 | 2021-11-23 | 2020-08-11 | 2022-03-16 | 2022-03-16 |  | 2022-03-18 | Sponsor
94 | 21/FT/0085 | 1003785 | A Dose-Escalation and Expansion Study of the Safety and Pharmacokinetics of XL092 as Single-Agent and Combination Therapy in Subjects with Inoperable Locally Advanced or Metastatic Solid Tumors |  | 2021-04-14 | 2022-01-31 | 2021-07-26 | 2022-05-16 | 2022-05-23 |  | 2022-05-25 | Both
95 | 21/SC/0293 | 301065 | Dose escalation study to evaluate the safety, tolerability, and anti-tumor activity of single agent IMU-935 in patients with progressive, metastatic castration resistant prostate cancer | 2021-12-09 | 2021-10-08 | 2021-11-10 | 2021-10-26 | 2021-11-19 | 2021-11-19 |  | 2021-11-26
96 | 21/LO/0693 | 1004042 | Study Evaluating Metastatic Castrate Resistant Prostate Cancer Treatment Using 177Lu-PNT2002 PSMA Therapy After Second-line Hormonal Treatment |  | 2021-10-04 | 2022-04-27 | 2022-02-08 | 2022-04-29 | 2022-04-29 |  | 2022-05-19
97 | 20/YH/0147 | 276888 | Pan Tumor Study for Long Term Follow-up of Cancer Survivors Who Have Participated in Trials Investigating Nivolumab | 2021-10-07 | 2020-04-15 | 2021-07-14 | 2020-07-17 | 2021-07-12 | 2021-07-16 |  | 2021-09-21 | Neither
98 | 19/NW/0046 | 227794 | A parallel arm, biomarker driven, phase II feasibility trial to determine the role of circulating tumour DNA in guiding a switch between targeted therapy and immune therapy in patients with advanced cutaneous melanoma |  | 2020-06-03 | 2021-07-14 | 2019-03-26 | 2021-07-08 | 2021-09-06 |  | 2021-09-09 | Sponsor
99 | 22/LO/0013 | 000000 | A Phase 2, Open-label, Multicenter, Cohort Study of ALKS 4230 Monotherapy Administered Subcutaneously in Patients With Advanced Cutaneous Melanoma or Intravenously in Patients With Advanced Mucosal Melanoma Who Have Previously Received Anti-PD-[L]1 Therapy - ARTISTRY-6 |  | 2022-01-07 | 2022-05-30
100 | 21/NW/0063 | 276314 | A European, multicenter, randomized, open-label, Phase II trial aiming to assess the clinical and biological activity of an anti-PD-L1 (atezolizumab) in operable localized soft tissue sarcomas patients to be treated with radiotherapy. |  | 2019-01-18 | 2021-10-07 | 2021-04-15 | 2021-10-08 | 2021-10-21 |  | 2022-02-14 | Neither
101 | 21/SC/0053 | 287444 | A Phase I, Open-label Multi-dose Two-Part Study to Characterize the Effects of a Strong CYP3A4 Inhibitor on the Steady-State Pharmacokinetics of Tazemetostat (EPZ-6438), and the Effects of a Strong CYP3A4 Inducer on the Steady-State Pharmacokinetics of Tazemetostat in Subjects with Advanced Malignancies |  | 2020-05-12 | 2021-07-15 | 2021-06-04 | 2021-08-23 | 2021-08-25 |  |  | Sponsor
102 | 21/SW/0038 | 1003680 | A Phase 2/3, Randomized, Multicenter Study to Evaluate AL102 in Patients with Progressing Desmoid Tumors | 2021-10-07 | 2021-03-19 | 2021-08-06 | 2021-05-13 | 2021-08-04 | 2021-08-10 |  | 2021-08-31
103 | 18/NI/0203 | 248385 | An Open-label, Crossover Study of the Effect of Food on the Pharmacokinetics of Paclitaxel Administered Orally as Oraxol | 2022-02-21 | 2021-03-29 | 2021-11-10 | 2019-01-16 | 2021-12-07 | 2021-12-09 |  | 2022-02-24 | Neither
104 | 21/FT/0113 | 300747 | A Randomized Multicenter Phase 3 Study of Milademetan Versus Trabectedin in Patients with Dedifferentiated Liposarcoma | 2021-12-30 | 2021-08-27 | 2021-11-09 | 2021-10-11 | 2021-12-07 | 2021-12-09 |  | 2021-12-17
105 | 21/SC/0377 | 1004109 | A pivotal trial of envafolimab, and envafolimab in combination with ipilimumab, in patients with advanced or metastatic undifferentiated pleomorphic sarcoma or myxofibrosarcoma who have progressed on prior chemotherapy |  | 2021-08-16 | 2022-03-16 | 2022-04-13 | 2022-04-08 | 2022-04-13 |  | 2022-04-27 | Neither
106 | 22/EM/0012 | 0 | A Randomized, Blinded, Placebo-controlled, Phase 2 Study of INBRX-109 in Unresectable or Metastatic Conventional Chondrosarcoma | 2022-05-16 | 2021-08-27 | 2022-04-12 | 2022-02-22 | 2022-04-14 | 2022-04-14 |  | 2022-04-29
107 | 20/SW/0016 | 263559 | A phase Ib/II study to assess the safety and activity of DURvalumab (MEDI4736) in combination with S-488210/S-488211 vAccine in Non-muscle invasive bladder CancEr |  | 2020-08-13 | 2022-04-19 | 2020-04-08 | 2022-04-29 | 2022-05-12 |  | 2022-06-13 | Neither
108 | 20/LO/1157 | 281627 | An open-label, randomized, controlled phase 3 study of enfortumab vedotin in combination with pembrolizumab with or without chemotherapy, versus chemotherapy alone in previously untreated locally advanced or metastatic urothelial cancer |  | 2020-10-07 | 2021-10-12 | 2020-12-17 | 2022-06-22 | 2022-06-23 |  |  | Sponsor
109 | 18/NW/0432 | 239796 | Safety and pharmacokinetics of ODM-208 in patients with metastatic castration-resistant prostate cancer |  | 2021-03-29 | 2021-07-19 | 2018-09-03 | 2021-08-25 | 2021-08-25 |  | 2021-09-20 | Neither
110 | 21/NW/0074 | 294508 | Phase 3 study investigating the efficacy and safety of TAVT-45 (abiraterone acetate) Granules for Oral Suspension (a novel abiraterone acetate formulation) relative to a reference abiraterone acetate formulation in patients with metastatic Castrate Sensitive Prostate Cancer (mCSPC) and metastatic Castrate Resistant Prostate Cancer (mCRPC) | 2021-12-29 | 2021-05-13 | 2021-09-01 | 2021-05-04 | 2021-10-04 | 2021-10-12 |  | 2021-10-25 | Neither
111 | 20/LO/1283 | 285961 | DASL-HiCaP: Darolutamide Augments Standard Therapy for Localised Very High-Risk Cancer of the Prostate (ANZUP1801). A randomised phase 3 double-blind, placebo-controlled trial of adding darolutamide to androgen deprivation therapy and definitive or salvage radiation in very high risk, clinically localised prostate cancer. |  | 2020-06-26 | 2021-12-14 | 2021-03-23 | 2022-01-13 | 2022-01-21 |  | 2022-03-07 | NHS Provider
112 | 21/LO/0509 | 295209 | A Dose Regimen-Finding Study to Evaluate the Safety, Tolerability, Pharmacokinetics, and Activity of Oradoxel Monotherapy in Subjects with Advanced Malignancies, delivered in a Modular Format. |  | 2021-04-19 | 2021-08-24 | 2021-08-23 | 2021-10-12 | 2021-10-13 |  | 2021-11-02 | Both
113 | 21/EM/0158 | 297323 | TALAPRO-3: A Phase 3, Randomized, Double-Blind, Study Of Talazoparib With Enzalutamide Versus Placebo With Enzalutamide In Men With DDR Gene Mutated Metastatic Castration-Sensitive Prostate Cancer | 2022-02-08 | 2021-04-09 | 2021-07-23 | 2021-08-13 | 2021-11-19 | 2021-11-19 |  | 2022-01-07 | NHS Provider
114 | 21/YH/0078 | 1003505 | A Randomized Open-Label Phase III Study of Sacituzumab Govitecan Versus Treatment of Physician’s Choice in Subjects with Metastatic or Locally Advanced Unresectable Urothelial Cancer | 2022-04-27 | 2021-05-13 | 2022-01-20 | 2021-05-14 | 2022-03-30 | 2022-04-05 |  | 2022-05-17 | Sponsor
115 | 21/FT/0073 | 296903 | An International Prospective Open-label, Randomized, Phase III Study comparing 177Lu-PSMA-617 in combination with Standard of Care, versus Standard of Care alone, in adult male patients with Metastatic Hormone Sensitive Prostate Cancer (mHSPC) |  | 2021-06-08 | 2021-12-07 | 2021-07-16 | 2022-03-31 | 2022-04-06 |  | 2022-05-06 | Sponsor
116 | 21/LO/0632 | 301120 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Phase III Study of Fuzuloparib Combined with Abiraterone Acetate and Prednisone (AA-P) versus Placebo Combined with AA-P as First-Line Treatment in Patients with Metastatic Castration-Resistant Prostate Cancer |  | 2021-02-19 | 2022-02-08 | 2022-02-08 | 2022-06-30 | 2022-06-30 |  |  | Sponsor
117 |  | 1005000 | A Phase III Double-Blind, Randomised, Placebo-Controlled Study Assessing the Efficacy and Safety of Capivasertib + Docetaxel Versus Placebo + Docetaxel as Treatment for Patients with Metastatic Castration Resistant Prostate Cancer (mCRPC) |  | 2022-03-28 | 2022-05-04